## Issue History
LONG STRATTON BYPASS
Date | General Description of Issue Details
2020-05-11 | Updated estimate based on drawing revisions P02

## QM
QUALITY MANAGEMENT
| Project No. | 70039894-CE1
| Project Title/Location | Long Stratton Bypass
| Estimate Stage | Updated estimate based on design drawing revisions P02
Rev | Status | Prepared by | Checked by | Date | Issued to | Company | Date | Transmission
0 | Issued | S. Whitaker | S Snowdon | 2020-05-11 | M Fox | WSP | 2020-05-11 | Via email
Formulas:
Date = [Date]

## Exec Summary
1. | EXECUTIVE SUMMARY
1.1 | OVERVIEW
WSP P&CS: Cost Planning & Estimating have been instructed to provide a cost plan for the
proposed works at Long Stratton Bypass.
Based on the level of design information provided, this cost estimate should be seen as an
order of magnitude estimate.
There is limited design information available therefore assumptions have been made in the
preparation of this cost plan where appropriate.
1.2 | RISKS
Typical risks that would normally be attributed to a project of this nature include;
- 3rd party interface issues including service providers, signalling providers and bus providers
- Delays in obtaining TRO's
- Changes to Regulations
- Discovery of UXO
- H&S issues on site
- Unidentified services
- Asbestos and other contaminants
- Severe adverse weather
- Site access / logistics
- Political Changes
- Delay in obtaining project approval / business case approval

## Basis of Estimate
2. | BASIS OF ESTIMATE
2.1 | MEASUREMENT AND QUANTIFICATION
This cost plan has been measured based on the Method of Measurement for Highway Works and has
been structured in accordance with the associated cost categories and group element formats.
The cost plan is based on quantities measured from drawings and information provided by the
design team.
2.2 | COST DATA
Costs based on 3Q2020 rates and no allowance has been made for tender price/building cost inflation.
All rates and prices are based on information from our in-house database
All rates and prices are nett of Contractors Fee/OH & P
All rates and prices have been adjusted to current values using BCIS indices
All costs are exclusive of VAT, Stamp Duty etc.
Where appropriate rates and prices cannot be applied to bespoke items, allowances have been made
for indicative purposes only.
Allowances for bespoke items are based on historical project data and would be subject to change
upon receipt of supplier quotes (if obtained)
A percentage wastage allowance has been included in the rates and / or quantities where appropriate
2.3 | BASE DATE
| The base date of this cost plan is | 3Q 2020
2.4 | PROGRAMME
To be confirmed
2.5 | RISK ALLOWANCE
All risk related costs and allowances should be based, wherever possible, on a detailed risk
and should have supporting information to the level of costing. As the amount of information
and level of assessment detail increases through progression of the project the risks should
be seen to reduce in line with the level of detail available.
During the early development stages of a project, cost estimates are based on the confidence
levels of the anticipated final cost. The anticipated final cost refers to the base cost estimate
with the addition of a risk allowance. At early design stages an allowance is applied to derive
the 85% confidence level (otherwise known as the P85).
The confidence level value risk allowances applied to the base cost estimate to derive the
PXX values are presented on the Cost Summary
No allowance has been included for Optimism Bias
2.6 | INFLATION
Costs based on 3Q2020 rates and no allowance has been made for tender price/building cost inflation.
2.7 | ASSUMPTIONS
General Caveats, Assumptions and Notes
Work can be carried out during normal working hours, unless otherwise stated
The high level budget cost have been prepared without the benefit of a GIS, Site Levels, Sectional Longitudinal Drawings or Construction Detail Section Through Drawings
The budget cost estimate only covers the anticipated works as outlined on the GA drawing identified on the drawing register tab
For scope of work refer to bils of quantities tabs
The cost estimate has been prepared without the benefit of a Contractror's programme so a percentage allowance has been included for Preliminaries and Traffic Management
An allownce of 20% has been included for Utilities costs, but excludes any cost for the diversion of high voltage cables
The allowance for Risk is 25% for this project, in lieu of a full risk analysis.
It has been assumed that this scheme is to be delivered as a 'stand alone' project.
Preliminaries
An allowance of 25% has been included for Preliminaries at 25% to take into consideration the anticipated reduced productivity as a result of the site conditions e.g. working around pedestrians, working around existing live services, etc.
Traffic Management
An allownce of 7% has been included for Traffic Management
2.8 | GENERAL SCOPE OF WORKS
Series 200: Site Clearance
An allowance for general site clearance has been made
Series 300: Fencing
Accoustic fencing has been included
An allowance has been made for temporary and permanent fencing
Series 500: Drainage
Prior to full drainage requirements being known, an assumption for drainage pipe and gullies
has been made
Series 600: Earthworks
Exisitng surface excavated to allow for the construction of revised carriageway and footpath
Excavated material will be used as fill on-site or disposed off-site
Series 700: Pavements
New carriageway assumed to be required across the site and revised road layout
Series 1100 : Kerbs, Footways and Paved Areas
New kerbs have been included
All new paved areas to footpaths finished off in black tarmac, not concrete or stone paving slabs
Series 1200: Traffic Signs and Road Markings
An allowance has been made for new road markings as not yet identified
An allowance has been made for road signs required on the site as not yet identified.
Series 2500 : Special Structures
An allowance has been included for installing 2nr uncontrolled pedestrian crossings
An allowance has been included for a new overbridge and a new footbridge
Series 3000 : Landscaping and Ecology
An allowance has been included for topsoil and grass seeding
2.9 | EXCLUSIONS
The following are excluded, but should be included within the overall Project Budget, where appropriate:
VAT, Stamp Duty, etc.
Any impact and restrictions relating to COVID-19
Any Ground Abnormalities
Enabling Works Cost
Diverting and rerouting existing public footpaths or rights of way
Inflation
Planning and Building Control Fees and associated costs
Costs associated with the demolition of exisitng structures on the site, it has been assumed that the site has been cleared
CPO for houses as it is anticipated this will not be required for the scheme
Costs associated with Statutory Fees (e.g. HMRI, Local Authority, etc.) unless confirmed
Costs associated with taxes and levies
Costs associated with licences and all associated costs and fees
Costs associated with changes in legislation and any form of applicable standards
Costs associated with invasive species, Japanese knotweed, Himalayan balsam
Costs associated with protected species such as great crested newts, badgers, bats and nesting birds
Costs associated with asbestos
Costs associated with the provision of anti-skid surfacing
Costs associated with Land Purchase/Value or compensation costs
Costs associated with out-of-hours working, unless otherwise stated
Costs associated with ongoing maintenance of Landscaped areas
Costs associated with Design Team fees
Costs associated with Consultation Workshops or Seminars
Costs associated with all other fees and survey costs
2.1 | OTHER ASSUMPTIONS/ CAVEATS
Based on attached drawing schedule
Rate for disposal off site allows for clean inert material only - allowed at £25/m3, unless otherwise advised
Surplus topsoil to remain on site for farmer use, deposited in stockpiles adjacent to work areas
Ground Bearing results do not require an additional capping layer

## Summary
| WSP |  |  | WSP
| Description - Long Stratton Bypass |  |  | 0
| Budget Cost Estimate Summary - 21 August 2020 |  |  | Budget Cost Estimate Summary 15.08.18
Ref.Nr |  | 3Q2020 | Ref.Nr |  | 3Q2018
|  | Total |  |  | Total
| Description | Amount |  | Description | Amount
| Miscellaneous |  |  | Miscellaneous
| Series 100 : Preliminaries | See Below |  | Series 100 : Preliminaries | See Below
| Series 200 : Site Clearance | 1065802 |  | Series 200 : Site Clearance | 1065802
| Series 300 : Fencing | 517344 |  | Series 300 : Fencing | 487778.5
| Series 400 : Road Restraints Systems (Vehicle and Pedestrian) | Excluded |  | Series 400 : Road Restraints Systems (Vehicle and Pedestrian) | Excluded
| Series 500 : Drainage (only) | 2495196.8025 |  | Series 500 : Drainage (only) | 2552453.0484
| Series 600 : Earthworks | 1499071.805 |  | Series 600 : Earthworks | 1427458.14
| Series 700 Pavements | 4314559.7 |  | Series 700 Pavements | 4151006.4426
| Series 1100 : Kerbs, Footways and Paved Areas | 398390.6 |  | Series 1100 : Kerbs, Footways and Paved Areas | 644289.284
| Series 1200 : Traffic Signs and Road Markings | 117691.5 |  | Series 1200 : Traffic Signs and Road Markings | 117691.5
| Series 1300 : Road Lighting Columns and Brackets, CCTV | Excluded |  | Series 1300 : Road Lighting Columns and Brackets, CCTV | Excluded
| Masts and Cantilever Masts |  |  | Masts and Cantilever Masts
| Series 1400 : Electrical Work for Road Lighting and Traffic Signs | Excluded |  | Series 1400 : Electrical Work for Road Lighting and Traffic Signs | Excluded
| Series 1500 : Motorway Communications | Excluded |  | Series 1500 : Motorway Communications | Excluded
| Series 1600 : Piling and Embedded Retaining Walls | Excluded |  | Series 1600 : Piling and Embedded Retaining Walls | Excluded
| Series 1700 : Structural Concrete | Excluded |  | Series 1700 : Structural Concrete | Excluded
| Series 1800 : Steelwork for Structures | Excluded |  | Series 1800 : Steelwork for Structures | Excluded
| Series 1900 : Protection of Steelwork against Corrosion | Excluded |  | Series 1900 : Protection of Steelwork against Corrosion | Excluded
| Series 2000 : Waterproofing for Structures | Excluded |  | Series 2000 : Waterproofing for Structures | Excluded
| Series 2100 : Bridge Bearings | Excluded |  | Series 2100 : Bridge Bearings | Excluded
| Series 2300 : Bridge Expansion Joints and Sealing of gaps | Excluded |  | Series 2300 : Bridge Expansion Joints and Sealing of gaps | Excluded
| Series 2400 : Brickwork, Blockwork and Stonework | Excluded |  | Series 2400 : Brickwork, Blockwork and Stonework | Excluded
| Series 2500 : Special Structures |  |  | Series 2500 : Special Structures
| Uncontrolled Pedestrain Crossing - 2Nr | 30000 |  | Uncontrolled Pedestrain Crossing - 2Nr | 30000
| Bridges, Headwalls and PROW Works | 3409097.22 |  | Bridges, Headwalls and PROW Works | 3569513.74
| Series 2700 : Accomodation Works, Works for Statutory | Excluded |  | Series 2700 : Accomodation Works, Works for Statutory | Excluded
| Undertakers |  |  | Undertakers
| Series 3000 : Landscaping and Ecology | 314400 |  | Series 3000 : Landscaping and Ecology | 314400
| Sub-total : Direct Works | 14161553.6275 |  | Sub-total : Direct Works | 14360392.655
| Prelims: Site Set up, Supervision, Overheads and other Associated Indirect Costs |  |  | Prelims: Site Set up, Supervision, Overheads and other Associated Indirect Costs
| HSEQ, and other Associated Indirect Costs : 25% | 3540388.4069 |  | HSEQ, and other Associated Indirect Costs : 25% | 3590098.1638
| Traffic Management: 7% | 991308.7539 |  | Traffic Management: 7% | 1005227.4859
| Sub - Total (A) | 18693250.7883 |  | Sub - Total (A) | 18955718.3046
| Profit : 8% | 1495460.0631 |  | Profit : 8% | 1516457.4644
| Utilities Cost - (20% of direct works) | 2832310.7255 |  | Utilities Cost - (20% of direct works) | 2872078.531
| Sub - Total (B) | 23021021.5769 |  | Sub - Total (B) | 23344254.3
| Risk / Contingency/Optimism Bias/Contingency : 25% | 5755255.3942 |  | Risk / Contingency/Optimism Bias/Contingency : 25% | 5836063.575
| Estimated Total Cost = | 28780000 |  | Estimated Total Cost = | 29190000

## BofQ Build-ups
WSP | [5 empty] | WSP
Description - Long Stratton Bypass |  |  |  | 2020-08-21 |  | Description - Long Stratton Bypass |  |  |  | 2018-04-04
Budget Estimate |  |  |  | Total |  | Budget Estimate |  |  |  | Total
Description | Quantity | Unit | Rate | Amount |  | Description | Quantity | Unit | Rate | Amount
Main Site Works | [5 empty] | Main Site Works
Site Clearance |  |  |  |  | 200 left as previous | Site Clearance
Site Clearance
General Site Clearance | [5 empty] | General Site Clearance
For Right of Way / Site Boundary : Open Field Site | 15 | hectare | 1920 | 28800 |  | For Right of Way / Site Boundary : Open Field Site | 15 | hectare | 1920 | 28800
For Right of Way / Site Boundary : Medium Density Wooded | 1 | hectare | 4000 | 4000 |  | For Right of Way / Site Boundary : Medium Density Wooded | 1 | hectare | 4000 | 4000
Live dual carriageway | 2.3 | hectare | 5940 | 13662 |  | Live dual carriageway | 2.3 | hectare | 5940 | 13662
Take up or down and remove to tip off site | [5 empty] | Take up or down and remove to tip off site
Precast Concrete Kerbs and Channels | 720 | m | 5 | 3600 |  | Precast Concrete Kerbs and Channels | 720 | m | 5 | 3600
Traffic Sign Including Post | 10 | nr | 74 | 740 |  | Traffic Sign Including Post | 10 | nr | 74 | 740
Remove existing carriageway to accommodate new - o/a thickness 600mm (assume contaminated material) | 14500 | m2 | 70 | 1015000 |  | Remove existing carriageway to accommodate new - o/a thickness 600mm (assume contaminated material) | 14500 | m2 | 70 | 1015000
Series 200 : Site Clearance |  |  |  | 1065802 |  | Series 200 : Site Clearance |  |  |  | 1065802
Series 300 : Fencing | [5 empty] | Series 300 : Fencing
Accoustic Fencing; noise reflective barrier; with accoustic timber planks post support system (2m high) | 482 | m2 | 175 | 84350 | 300 left as previous apart from accoustic | Accoustic Fencing; noise reflective barrier; with accoustic timber planks post support system (2m high) | 458 | m2 | 175 | 80150
Temporary Site Boundary Fencing; Type 2 1.275high , timber post and two strands of galv barbed wire and four strands of galv plain wire | [5 empty] | Temporary Site Boundary Fencing; Type 2 1.275high , timber post and two strands of galv barbed wire and four strands of galv plain wire
with 50x50x3mm plastic coated RHS posts Bypass only | 8276 | m | 14.15 | 117105.4 |  | with 50x50x3mm plastic coated RHS posts Bypass only | 8276 | m | 14.15 | 117105.4
Permanent Site Boundary Fencing : Timber Rail Fencing | [5 empty] | Permanent Site Boundary Fencing : Timber Rail Fencing
1.400 metre high : timber posts and Four rails Bypass & Link Roads | 11264 | m | 26.15 | 294553.6 |  | 1.400 metre high : timber posts and Four rails Bypass & Link Roads | 10294 | m | 26.15 | 269188.1
Post and wire Perimeter Fence to attenuation lagoons | 1095 | m | 15 | 16425 |  | Post and wire Perimeter Fence to attenuation lagoons | 1095 | m | 15 | 16425
Post and wire Perimeter Fence to oil containment ditch | 144 | m | 15 | 2160 |  | Post and wire Perimeter Fence to oil containment ditch | 144 | m | 15 | 2160
Access Gates to ponds | 11 | nr | 250 | 2750 |  | Access Gates to ponds | 11 | nr | 250 | 2750
Series 300 : Fencing |  |  |  | 517344 |  | Series 300 : Fencing |  |  |  | 487778.5
Series 500 : Drainage and Service Ducts | [5 empty] | Series 500 : Drainage and Service Ducts
Drainage to Bypass and Link Roads | [5 empty] | Drainage to Bypass and Link Roads
Drain runs not exceeding 2m deep to the following diameters; | [5 empty] | Drain runs not exceeding 2m deeep to the following diameters;
150mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 818 | m | 90 | 73620 |  | 150mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 818 | m | 90 | 73620
150mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 818 | m | 65 | 53170 |  | 150mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 818 | m | 65 | 53170
225mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 170 | m | 100 | 17000 |  | 225mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 170 | m | 100 | 17000
225mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 170 | m | 70 | 11900 |  | 225mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 170 | m | 70 | 11900
300mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 81 | m | 110 | 8910 |  | 300mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 81 | m | 110 | 8910
300mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 81 | m | 80 | 6480 |  | 300mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 81 | m | 80 | 6480
450mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 538 | m | 185 | 99530 |  | 450mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 538 | m | 185 | 99530
450mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 538 | m | 130 | 69940 |  | 450mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 538 | m | 130 | 69940
525mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 82 | m | 210 | 17220 |  | 525mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 82 | m | 210 | 17220
525mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 82 | m | 150 | 12300 |  | 525mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 82 | m | 150 | 12300
600mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 245 | m | 245 | 60025 |  | 600mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 245 | m | 245 | 60025
600mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 245 | m | 180 | 44100 |  | 600mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 245 | m | 180 | 44100
Geotextile/terram route guard membrane to drain run | 13551 | m2 | 3.46 | 46886.46 |  | Geotextile/terram route guard membrane to drain run | 13551 | m2 | 3.46 | 46886.46
175mm thick reinforced concrete slab over drain | 490 | m3 | 150 | 73500 |  | 175mm thick reinforced concrete slab over drain | 490 | m3 | 150 | 73500
Mesh reinforcement single layer; A142 | 2798 | m2 | 6.5 | 18187 |  | Mesh reinforcement single layer; A142 | 2798 | m2 | 6.5 | 18187
Formwork Class F2:300mm wide or less at any inclination | 3868 | m2 | 95 | 367460 |  | Formwork Class F2:300mm wide or less at any inclination | 3868 | m2 | 95 | 367460
Chambers: 1200mm internal diam to the following depth range: | [5 empty] | Chambers: 1200mm internal diam to the following depth range:
Depth nt exc 1m | 17 | nr | 1500 | 25500 |  | Depth nt exc 1m | 17 | nr | 1500 | 25500
Depth 1m to 2m | 132 | nr | 1875 | 247500 |  | Depth 1m to 2m | 132 | nr | 1875 | 247500
Depth 2m to 3m | 1 | nr | 2380 | 2380 |  | Depth 2m to 3m | 1 | nr | 2380 | 2380
Road gully | 146 | nr | 600 | 87600 |  | Road gully | 146 | nr | 600 | 87600
Filter Drains to Road Verge | [5 empty] | Filter Drains to Road Verge
Excavation of acceptable material excluding Class 5A & dispose in temporary spoil heaps | 5867 | m3 | 10 | 58670 | as 2018 estimate except this | Excavation of acceptable material excluding Class 5A & dispose in temporary spoil heaps | 5550.3308 | m3 | 10 | 55503.3075
Geotextile guard membrane to filter drain | 30508.4 | m2 | 3.46 | 105559.064 | as 2018 estimate except this | Geotextile guard membrane to filter drain | 59971.677 | m2 | 3.46 | 207502.0024
Imported fill ; granular material to clause 505 | 5867 | m3 | 35 | 205345 | as 2018 estimate except this | Imported fill ; granular material to clause 505 | 5550 | m3 | 35 | 194250
Concrete Carrier pipe to base of filter drain to the following diam: | [5 empty] | Concrete Carrier pipe to base of filter drain to the following diam:
300mm - split between pipe sizes estimated | 3000 | m | 15 | 45000 | as 2018 estimate except this | 300mm | 2550 | m | 15 | 38250
450mm | 2867 | m | 25 | 71675 | as 2018 estimate except this | 450mm | 2082 | m | 25 | 52050
Rerouting Existing Ditch Incl 450mm diam pipe. | [5 empty] | Rerouting Existing Ditch Incl 450mm diam pipe.
Excavate to formation and dispose in temporary spoil heaps | 284.28 | m3 | 10 | 2842.8 |  | Excavate to formation and dispose in temporary spoil heaps | 284.28 | m3 | 10 | 2842.8
Install Geotextile to line ditch | 1102.1 | m2 | 3.46 | 3813.266 |  | Install Geotextile to line ditch | 1102.1 | m2 | 3.46 | 3813.266
Granular bed and surround | 206 | m | 35 | 7210 |  | Granular bed and surround | 206 | m | 35 | 7210
450mm diam pipe | 206 | m | 25 | 5150 |  | 450mm diam pipe | 206 | m | 25 | 5150
Backfill with suitable material | 236.9 | m3 | 35 | 8291.5 |  | Backfill with suitable material | 236.9 | m3 | 35 | 8291.5
Existing Ditches to be Piped beneath Poposed Bypass | [5 empty] | Existing Ditches to be Piped beneath Poposed Bypass
450mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 538 | m | 185 | 99530 |  | 450mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 538 | m | 185 | 99530
Install Geotextile to line ditch | 3206.225 | m2 | 2.5 | 8015.5625 |  | Install Geotextile to line ditch | 3206.225 | m2 | 2.5 | 8015.5625
Outfall Drain Under Road | [5 empty] | Outfall Drain Under Road
300mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 60 | m | 110 | 6600 |  | 300mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 60 | m | 110 | 6600
300mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 60 | m | 80 | 4800 |  | 300mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 60 | m | 80 | 4800
450mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 7 | m | 185 | 1295 |  | 450mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 7 | m | 185 | 1295
450mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 7 | m | 130 | 910 |  | 450mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 7 | m | 130 | 910
525mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 6 | m | 210 | 1260 |  | 525mm dia depth to invert nt exc 2m with Type Z bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 6 | m | 210 | 1260
525mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 6 | m | 150 | 900 |  | 525mm dia depth to invert nt exc 2m with Type S bed and surround in trench depth to invert not exceeding 2 metres average depth to invert 1.250 metres | 6 | m | 150 | 900
175mm thick reinforced concrete slab over drain | 18 | m3 | 150 | 2700 |  | 175mm thick reinforced concrete slab over drain | 18 | m3 | 150 | 2700
Mesh reinforcement single layer; A142 | 102 | m2 | 6.5 | 663 |  | Mesh reinforcement single layer; A142 | 102 | m2 | 6.5 | 663
Formwork Class F2:300mm wide or less at any inclination | 146 | m2 | 95 | 13870 |  | Formwork Class F2:300mm wide or less at any inclination | 146 | m2 | 95 | 13870
Install Geotextile to line ditch | 490 | m2 | 3.46 | 1695.4 |  | Install Geotextile to line ditch | 490 | m2 | 3.46 | 1695.4
Others: | [5 empty] | Others:
Stopping up/removing exisiting ditches | 1057 | m | 6.75 | 7134.75 |  | Stopping up/removing exisiting ditches | 1057 | m | 6.75 | 7134.75
Formation of Ponds & Oil Containment Ditches; assumed depth 2m / 45% slope sides ) | [5 empty] | Formation of Ponds & Oil Containment Ditches; assumed depth 2m / 45% slope sides )
Excavation | 20735 | m3 | 5 | 103675 |  | Excavation | 20735 | m3 | 5 | 103675
Disposal in spoil heaps | 20735 | m3 | 10 | 207350 |  | Disposal in spoil heaps | 20735 | m3 | 10 | 207350
Level & compact formation | 10775 | m2 | 1 | 10775 |  | Level & compact formation | 10775 | m2 | 1 | 10775
Pond liner | 10775 | m2 | 4 | 43100 |  | Pond liner | 10775 | m2 | 4 | 43100
Edge detail | 1159 | m | 12 | 13908 |  | Edge detail | 1159 | m | 12 | 13908
Allowance ecology measures | 1 | item | 12000 | 12000 |  | Allowance ecology measures | 1 | item | 12000 | 12000
Forming Ditches | [5 empty] | Forming Ditches
Excavation | 3240 | m3 | 5 | 16200 |  | Excavation | 3240 | m3 | 5 | 16200
Disposal in spoil heaps | 3240 | m3 | 10 | 32400 |  | Disposal in spoil heaps | 3240 | m3 | 10 | 32400
Grading Slopes | 9600 | m2 | 2.5 | 24000 |  | Grading Slopes | 9600 | m2 | 2.5 | 24000
Headwall ( pipe accesses ) | 57 | nr | 450 | 25650 | as 2018 estimate except this | Headwall ( pipe accesses ) | 48 | nr | 450 | 21600
Series 500 : Drainage |  |  |  | 2495196.8025 |  | Series 500 : Drainage |  |  |  | 2552453.0484
Series 600 : Earthworks | [5 empty] | Series 600 : Earthworks
Excavation | [5 empty] | Excavation
Typical Motorway Cutting generally using motorised scrapers | [5 empty] | Typical Motorway Cutting generally using motorised scrapers
and/or dozers on an average haul of 2000 metres (one way) | [5 empty] | and/or dozers on an average haul of 2000 metres (one way)
Excavation of acceptable material Class 5A - Topsoil (250mm thick) | 41451.5 | m3 | 1.65 | 68394.975 |  | Excavation of acceptable material Class 5A - Topsoil (250mm thick) | 37154 | m3 | 1.65 | 61304.1
Deposit into temporary spoil heaps | 41451.5 | m3 | 4.52 | 187360.78 |  | Deposit into temporary spoil heaps | 37154 | m3 | 4.52 | 167936.08
Excavation of acceptable material excluding Class 5A | [5 empty] | Excavation of acceptable material excluding Class 5A
in Cutting and Other excavation | 52157 | m3 | 3.76 | 196110.32 | as 2018 estimate | in Cutting and Other excavation | 52157 | m3 | 3.76 | 196110.32
Deposit into temporary spoil heaps | 52157 | m3 | 4.52 | 235749.64 | as 2018 estimate | Deposit into temporary spoil heaps | 52157 | m3 | 4.52 | 235749.64
Excavation of acceptable material excluding Class 5A - filter drain | included elsewhere |  | 2.5 |  |  | Excavation of acceptable material excluding Class 5A - filter drain | 5500 | m3 | 2.5 | 13750
Deposit into temporary spoil heaps | 5867 | m3 | 4.52 | 26518.84 |  | Deposit into temporary spoil heaps | 5500 | m3 | 4.52 | 24860
Deposition of Fill | [5 empty] | Deposition of Fill
Deposition of acceptable material taken from spoil heaps to general areas and earth bund mounds, embankments and other areas of fill | 57657 | m3 | 2.5 | 144142.5 | as 2018 estimate | Deposition of acceptable material taken from spoil heaps to general areas and earth bund mounds, embankments and other areas of fill | 57657 | m3 | 2.5 | 144142.5
Deposition of acceptable topsoil material taken from spoil heaps to embankment and verge areas only (250mm thick) | 25116 | m3 | 2.5 | 62790 |  | Deposition of acceptable material taken from spoil heaps to general areas and earth bund mounds, embankments and other areas of fill | 0 | m3 | 2.5 | 0
Remove surplus acceptable material off site | 367 | m3 | 25 | 9175 |  | Remove surplus acceptable material off site | 0 | m3 | 25 | 0
Fill with suitable imported Material | 14152 | m3 | 35 | 495320 | as 2018 estimate | Fill with suitable imported Material | 14152 | m3 | 35 | 495320
Disposal Of Material | [5 empty] | Disposal Of Material
Dispose of acceptable material Class 5A (Topsoil 150mm thick): 10-Tonne tipping | [5 empty] | Dispose of acceptable material Class 5A (Topsoil 150mm thick): 10-Tonne tipping
Lorry : On/Off Site : To tip N.Exc. 1.000 km | 15580.5 | m3 | 4.5 | 70112.25 |  | Lorry : On/Off Site : To tip N.Exc. 1.000 km | 18864 | m3 | 4.5 | 84888
Dispose of acceptable material Class 5A (Topsoil 150mm thick): 10-Tonne tipping | [5 empty] | Dispose of acceptable material Class 5A (Topsoil 150mm thick): 10-Tonne tipping
Lorry : On/Off Site : To tip N.Exc. 1.000 km to RBs in 4nr | 755 | m3 | 4.5 | 3397.5 | as 2018 estimate | Lorry : On/Off Site : To tip N.Exc. 1.000 km to RBs in 4nr | 755 | m3 | 4.5 | 3397.5
Series 600 : Earthworks |  |  |  | 1499071.805 |  | Series 600 : Earthworks |  |  |  | 1427458.14
Series 700 Pavements | [5 empty] | Series 700 Pavements
Bypass & Traffic Islands | [5 empty] | Bypass & Traffic Islands
Sub-base in carriageway, hard shoulder and hardstrip | [5 empty] | Sub-base in carriageway, hard shoulder and hardstrip
450mm deep | 22980.6 | m3 | 38 | 873262.8 |  | 450mm deep | 20986.4611 | m3 | 38 | 797485.5201
100mm deep | 87.4 | m3 | 40 | 3496 |  | 100mm deep | 61.565 | m3 | 40 | 2462.6
Dense Bitumen Macadam | [5 empty] | Dense Bitumen Macadam
230mm Base course | 51068 | m2 | 35 | 1787380 |  | 230mm Base course | 43659.1914 | m2 | 35 | 1528071.6999
60mm Binder course | 51068 | m2 | 13.5 | 689418 |  | 60mm Binder course | 43659.1914 | m2 | 13.5 | 589399.0842
50mm Binder course (Traffic island) | 874 | m2 | 11 | 9614 |  | 50mm Binder course (Traffic island) | 776.37 | m2 | 11 | 8540.07
40mm Surface course | 51068 | m2 | 12 | 612816 |  | 40mm Surface course | 43659.1914 | m2 | 12 | 523910.2971
20mm Surface course (Traffic Island) | 874 | m2 | 10 | 8740 |  | 20mm Surface course (Traffic Island) | 776.37 | m2 | 10 | 7763.7
Link Roads | [5 empty] | Link Roads
Sub-base in carriageway, hard shoulder and hardstrip | [5 empty] | Sub-base in carriageway, hard shoulder and hardstrip
450mm deep | 2087.55 | m3 | 38 | 79326.9 |  | 450mm deep | 5943.6093 | m3 | 38 | 225857.1553
100mm deep | 463.9 | m3 | 35 | 16236.5 |  | 100mm deep | 0 | m3 | 35 | 0
Dense Bitumen Macadam | [5 empty] | Dense Bitumen Macadam
150mm Base course | 4639 | m2 | 25 | 115975 |  | 150mm Base course | 217 | m2 | 25 | 5425
60mm Binder course | 4639 | m2 | 13.5 | 62626.5 |  | 60mm Binder course | 217 | m2 | 13.5 | 2929.5
40mm Surface course | 4639 | m2 | 12 | 55668 |  | 40mm Surface course | 217 | m2 | 12 | 2604
[6 empty] | Geotextile to bypass, link roads and filter drains | 131953.126 | m2 | 3.46 | 456557.816
Series 700 Pavements |  |  |  | 4314559.7 |  | Series 700 Pavements |  |  |  | 4151006.4426
Series 1100 : Kerbs, Footways and Paved Areas | [5 empty] | Series 1100 : Kerbs, Footways and Paved Areas
Link Roads, Footpaths, Cycleways and Roundabouts | [5 empty] | Link Roads, Footpaths, Cycleways and Roundabouts
125 x 225 HB2 road kerbs: striaght or curved exc 12 m radius | 2970 | m | 30 | 89100 |  | 125 x 225 HB2 road kerbs: striaght or curved exc 12 m radius | 5157.8488 | m | 30 | 154735.464
125 x 225 HB2 road kerbs: striaght or curved not exc 12 m radius | 853 | m | 30 | 25590 | roundabouts + islands | 125 x 225 HB2 road kerbs: striaght or curved not exc 12 m radius | 489.17 | m | 30 | 14675.1
125 x 225/150 DK dropped road kerbs: striaght or curved exc 12 m radius | 169.28 | m | 35 | 5924.8 |  | 125 x 225/150 DK dropped road kerbs: striaght or curved exc 12 m radius | 169.28 | m | 35 | 5924.8
125 x 225/150 BN bull nosed road kerbs: striaght or curved exc 12 m radius | 169.28 | m | 35 | 5924.8 |  | 125 x 225/150 BN bull nosed road kerbs: striaght or curved exc 12 m radius | 169.28 | m | 35 | 5924.8
50 x 150 flat top Pcc edging to footpaths | 3314 | m | 18 | 59652 |  | 50 x 150 flat top Pcc edging to footpaths | 3936.99 | m | 18 | 70865.82
Footways | [5 empty] | Footways
100 mm Sub-base | 876.4 | m3 | 40 | 35056 |  | 100 mm Sub-base | 6474.6922 | m3 | 40 | 258987.688
50mm Binder Course | 8764 | m2 | 11 | 96404 |  | 50mm Binder Course | 6472.4806 | m2 | 11 | 71197.2866
20mm Surface Course | 8764 | m2 | 9 | 78876 |  | 20mm Surface Course | 6472.4806 | m2 | 9 | 58252.3254
450 x 450 tactile paving slab | 74.52 | m2 | 25 | 1863 |  | 450 x 450 tactile paving slab | 149.04 | m2 | 25 | 3726
Series 1100 : Kerbs, Footways and Paved Areas |  |  |  | 398390.6 |  | Series 1100 : Kerbs, Footways and Paved Areas |  |  |  | 644289.284
Series 1200 : Traffic Signs and Road Markings | [5 empty] | Series 1200 : Traffic Signs and Road Markings
Traffic Signs | [5 empty] | Traffic Signs
TSR510 Roundabout ahead 322m to give way line - single post | 1 | nr | 250 | 250 |  | TSR510 Roundabout ahead 322m to give way line - single post | 1 | nr | 250 | 250
Advance directional sign 215m to give way line - triple post | 1 | nr | 2500 | 2500 |  | Advance directional sign 215m to give way line - triple post | 1 | nr | 2500 | 2500
Directionnal flag sign - double post | 3 | nr | 425 | 1275 |  | Directionnal flag sign - double post | 3 | nr | 425 | 1275
Advance directional sign 70m to give way line - triple post | 1 | nr | 2500 | 2500 |  | Advance directional sign 70m to give way line - triple post | 1 | nr | 2500 | 2500
TSR510 Roundabout ahead 105m to give way line - single post | 1 | nr | 250 | 250 |  | TSR510 Roundabout ahead 105m to give way line - single post | 1 | nr | 250 | 250
TSR 816 No through road - single post | 2 | nr | 250 | 500 |  | TSR 816 No through road - single post | 2 | nr | 250 | 500
TSR 671 - single post | 2 | nr | 250 | 500 |  | TSR 671 - single post | 2 | nr | 250 | 500
TSR 670 - single post 30mph | 1 | nr | 250 | 250 |  | TSR 670 - single post 30mph | 1 | nr | 250 | 250
TSR 610 - Illuminsted bollard | 3 | nr | 500 | 1500 |  | TSR 610 - Illuminsted bollard | 3 | nr | 500 | 1500
TSR 606 single post | 3 | nr | 250 | 750 |  | TSR 606 single post | 3 | nr | 250 | 750
TSR 515 - double post | 6 | nr | 750 | 4500 |  | TSR 515 - double post | 6 | nr | 750 | 4500
Advance directional sign 215m to give way line - triple post | 1 | nr | 2500 | 2500 |  | Advance directional sign 215m to give way line - triple post | 1 | nr | 2500 | 2500
TSR 610 - Illuminsted bollard | 4 | nr | 500 | 2000 |  | TSR 610 - Illuminsted bollard | 4 | nr | 500 | 2000
Directionnal flag sign - double post | 4 | nr | 1200 | 4800 |  | Directionnal flag sign - double post | 4 | nr | 1200 | 4800
TSR 606 single post | 4 | nr | 250 | 1000 |  | TSR 606 single post | 4 | nr | 250 | 1000
TSR 515 - double post | 8 | nr | 750 | 6000 |  | TSR 515 - double post | 8 | nr | 750 | 6000
TSR 671 - single post | 2 | nr | 250 | 500 |  | TSR 671 - single post | 2 | nr | 250 | 500
TSR 670 - single post 30mph | 2 | nr | 250 | 500 |  | TSR 670 - single post 30mph | 2 | nr | 250 | 500
TSR510 Roundabout ahead 105m to give way line - single post | 1 | nr | 250 | 250 |  | TSR510 Roundabout ahead 105m to give way line - single post | 1 | nr | 250 | 250
Advance directional sign 70m to give way line - triple post | 1 | nr | 2500 | 2500 |  | Advance directional sign 70m to give way line - triple post | 1 | nr | 2500 | 2500
Advance directional sign 215m to give way line - triple post | 2 | nr | 2500 | 5000 |  | Advance directional sign 215m to give way line - triple post | 2 | nr | 2500 | 5000
TSR510 Roundabout ahead 322m to give way line - single post | 2 | nr | 250 | 500 |  | TSR510 Roundabout ahead 322m to give way line - single post | 2 | nr | 250 | 500
TSR 610 - Illuminsted bollard | 3 | nr | 500 | 1500 |  | TSR 610 - Illuminsted bollard | 3 | nr | 500 | 1500
Directionnal flag sign - double post | 3 | nr | 1200 | 3600 |  | Directionnal flag sign - double post | 3 | nr | 1200 | 3600
TSR 606 single post | 3 | nr | 250 | 750 |  | TSR 606 single post | 3 | nr | 250 | 750
TSR 515 - double post | 6 | nr | 750 | 4500 |  | TSR 515 - double post | 6 | nr | 750 | 4500
Advance directional sign 70m to give way line - triple post | 1 | nr | 2500 | 2500 |  | Advance directional sign 70m to give way line - triple post | 1 | nr | 2500 | 2500
TSR 671 - single post | 2 | nr | 250 | 500 |  | TSR 671 - single post | 2 | nr | 250 | 500
TSR 670 - single post 20mph | 1 | nr | 250 | 250 |  | TSR 670 - single post 20mph | 1 | nr | 250 | 250
TSR 670 - single post 50mph | 1 | nr | 250 | 250 |  | TSR 670 - single post 50mph | 1 | nr | 250 | 250
Advance directional sign 160m to give way line - triple post | 2 | nr | 2500 | 5000 |  | Advance directional sign 160m to give way line - triple post | 2 | nr | 2500 | 5000
Advance directional sign 215m to give way line - double post | 2 | nr | 1200 | 2400 |  | Advance directional sign 215m to give way line - double post | 2 | nr | 1200 | 2400
TSR510 Roundabout ahead 240m to give way line - single post | 1 | nr | 250 | 250 |  | TSR510 Roundabout ahead 240m to give way line - single post | 1 | nr | 250 | 250
TSR 610 - Illuminsted bollard | 1 | nr | 500 | 500 |  | TSR 610 - Illuminsted bollard | 1 | nr | 500 | 500
TSR 670 - single post 30mph | 1 | nr | 250 | 250 |  | TSR 670 - single post 30mph | 1 | nr | 250 | 250
TSR 670 - single post 50mph | 1 | nr | 250 | 250 |  | TSR 670 - single post 50mph | 1 | nr | 250 | 250
TSR 816 No through road - single post | 1 | nr | 250 | 250 |  | TSR 816 No through road - single post | 1 | nr | 250 | 250
Advance directional sign 160m to give way line - triple post | 1 | nr | 2500 | 2500 |  | Advance directional sign 160m to give way line - triple post | 1 | nr | 2500 | 2500
Directionnal sign - single post | 1 | nr | 250 | 250 |  | Directionnal sign - single post | 1 | nr | 250 | 250
TSR 610 - Illuminsted bollard | 4 | nr | 500 | 2000 |  | TSR 610 - Illuminsted bollard | 4 | nr | 500 | 2000
Directionnal flag sign - double post | 4 | nr | 1200 | 4800 |  | Directionnal flag sign - double post | 4 | nr | 1200 | 4800
TSR 606 single post | 4 | nr | 250 | 1000 |  | TSR 606 single post | 4 | nr | 250 | 1000
TSR 515 - double post | 8 | nr | 750 | 6000 |  | TSR 515 - double post | 8 | nr | 750 | 6000
TSR 670 - single post 30mph | 2 | nr | 250 | 500 |  | TSR 670 - single post 30mph | 2 | nr | 250 | 500
TSR 670 - single post 50mph | 2 | nr | 250 | 500 |  | TSR 670 - single post 50mph | 2 | nr | 250 | 500
Advance directional sign 160m to give way line - triple post | 1 | nr | 2500 | 2500 |  | Advance directional sign 160m to give way line - triple post | 1 | nr | 2500 | 2500
Advance directional sign 70m to give way line - triple post | 1 | nr | 2500 | 2500 |  | Advance directional sign 70m to give way line - triple post | 1 | nr | 2500 | 2500
TSR510 Roundabout ahead 105m to give way line - single post | 1 | nr | 250 | 250 |  | TSR510 Roundabout ahead 105m to give way line - single post | 1 | nr | 250 | 250
Road Markings | [5 empty] | Road Markings
150mm wide edge marking in reflectorized white; thermoplastic | 6766 | m | 1.5 | 10149 |  | 150mm wide edge marking in reflectorized white | 6766 | m | 1.5 | 10149
150mm wide to centre of bypass and link roads marking in reflectorized white; thermoplastic | 3827 | m | 1.5 | 5740.5 |  | 150mm wide to centre of bypass and link roads marking in reflectorized white | 3827 | m | 1.5 | 5740.5
150mm wide to roundabout islands in reflectorized white; thermoplastic | 1805 | m | 1.5 | 2707.5 |  | 150mm wide to roundabout islands in reflectorized white | 1805 | m | 1.5 | 2707.5
150mm wide to roundabouts in reflectorized white; thermoplastic | 643 | m | 1.5 | 964.5 |  | 150mm wide to roundabouts in reflectorized white | 643 | m | 1.5 | 964.5
Arrows in reflectorized white; 16m long double headed; thermoplastic | 1 | nr | 110 | 110 |  | Arrows in reflectorized white; 16m long double headed | 1 | nr | 110 | 110
Triangles in reflectorized white; thermoplastic | 2 | nr | 35 | 70 |  | Triangles in reflectorized white; | 2 | nr | 35 | 70
Road Studs | [5 empty] | Road Studs
100 x 100mm square bi-directional with amber corner cube | 350 | nr | 8.87 | exc |  | 100 x 100mm square bi-directional with amber corner cube | 350 | nr | 8.87 | exc
Reflectors | [5 empty] | Reflectors
Bollards | [5 empty] | Bollards
Bollards to traffic islands | 15 | nr | 550 | 8250 |  | Bollards to traffic islands | 15 | nr | 550 | 8250
Timber bollards | 17 | nr | 225 | 3825 |  | Timber bollards | 17 | nr | 225 | 3825
Series 1200 : Traffic Signs and Road Markings |  |  |  | 117691.5 |  | Series 1200 : Traffic Signs and Road Markings |  |  |  | 117691.5
Series 1300 : Road Lighting Columns and Brackets, CCTV Masts | [5 empty] | Series 1300 : Road Lighting Columns and Brackets, CCTV Masts
and Cantilever Masts | [5 empty] | and Cantilever Masts
Excluded |  |  |  |  | as 2018 estimate | Excluded
Series 1300 : Road Lighting Columns and Brackets, CCTV Masts and Cantilever Masts |  |  |  | 0 |  | Series 1300 : Road Lighting Columns and Brackets, CCTV Masts and Cantilever Masts |  |  |  | 0
Series 1400 : Electrical Work for Road Lighting & | [5 empty] | Series 1400 : Electrical Work for Road Lighting &
Traffic Signs | [5 empty] | Traffic Signs
Excluded |  |  |  |  | as 2018 estimate | Excluded
Series 1400 : Electrical Work for Road Lighting and Traffic Signs |  |  |  | 0 |  | Series 1400 : Electrical Work for Road Lighting and Traffic Signs |  |  |  | 0
Series 2700 : Works for statutory Undertakers | [5 empty] | Series 2700 : Works for statutory Undertakers
Lowering or diversion of exisitng Statutory Services - Excluded |  |  |  |  | as 2018 estimate | Lowering or diversion of exisitng Statutory Services - Excluded
Series 2700 : Works for statutory Undertakers |  |  |  | 0 |  | Series 2700 : Works for statutory Undertakers |  |  |  | 0
Series 3000 : Landscape and Ecology | [5 empty] | Series 3000 : Landscape and Ecology
Rake and level topsoil | 125760 | m2 | 1.5 | 188640 | as 2018 estimate | Rake and level topsoil | 125760 | m2 | 1.5 | 188640
Grass seeding | 125760 | m2 | 1 | 125760 | as 2018 estimate | Grass seeding | 125760 | m2 | 1 | 125760
Series 3000 : Landscape and Ecology |  |  |  | 314400 |  | Series 3000 : Landscape and Ecology |  |  |  | 314400

## Series 2500 Special Struc
|  | Item | Description - Long Stratton Bypass | Qty | Unit | Rate | Amount
New Footpath to either side of footbridge (120m each side)
Series 600 : Earthworks
Excavation
|  |  | Excavation of acceptable material Class 5A - Topsoil (250mm thick) | 297.5 | m3 | 1.65 | 490.875
|  |  | Deposit into temporary spoil heaps | 297.5 | m3 | 4.52 | 1344.7
|  |  | Remove surplus acceptable material off site | 297.5 | m3 | 25 | 7437.5
Series 1100 : Kerbs, Footways and Paved Areas
Footways
|  |  | 100 mm Sub-base | 175 | m3 | 40 | 7000
|  |  | 50mm Binder Course | 1750 | m2 | 11 | 19250
|  |  | 20mm Surface Course | 1750 | m2 | 9 | 15750
|  |  | 50 x 150 flat top Pcc edging to footpaths | 875 | m | 18 | 15750
Series 2500 : Special Structures
New Foot Bridge
Length 30m
Width 4m
Series 600 : Earthworks
|  |  | Fill with suitable material to form ramps to footbridge | 11460 | m3 | 35 | 401100
Series 500 Drainage and Service Ducts
4 | 30 | 120 | Cable duct, 1x100mm dia, depth not exceeding 1.5m, in verges and central reserves | 120 | m | 8 | 960
Series 400 Road Restraint Systems
2 | 45 | 90 | Metal parapet railings, Group P5; 1.25m | 90 | m | 450 | 40500
|  |  | Safety fence connectors | 4 | no | 175 | 700
Series 700 Pavement
| 45 |  | Tarmac | 180 | m2 | 20 | 3600
| 4 | 180
Series 1100 Kerbs, Footway and Paved Areas
Combined kerb and drainage block Beany System
Foundation to Kerbs, etc
|  |  | Mass Concrete : 450 x 150mm to kerbs | 90 | m | 8.55 | 769.5
|  |  | 100 x 100 Haunching (Per Side) | 180 | m | 0.93 | 167.4
2 | 45 | 90 | Kerbs : top block, shallow base unit, stanadard cover plate and frame: laid straight or curved exceedig 12m radius | 90 | m | 140 | 12600
Series 1600 : Piling and Embedded Retaining Walls
|  |  | Establishment of piling plant for cast in place | 1 | item | 10000 | 10000
concrete piles (CFA)
|  |  | Moving piling plant for 600mm diameter bored piles | 87 | nr | 45 | 3915
8 | 20 | 160 | Vertical 600 mm diameter cast in place piles exceeding 15m in length but not exceeding 20m in length in main piling | 160 | m | 65 | 10400
8 | 20 | 160 | Vertical 600 mm diameter empty bores in main piling (provisional allowance) | 160 | m | 35 | 5600
|  |  | Cutting off surplus length of pile (assume 2m) | 16 | m | 30 | 480
|  |  | Preparing pile heads | 8 | nr | 30 | 240
|  |  | Establishment of proof loading equipment | 1 | item | 1700 | 1700
|  |  | Proof loading of vertical 600mm piles - say 10% | 8 | nr | 4060 | 32480
Series 1700 Structural Concrete
Pile Caps
8 x 5 x 1.2
2 | 4 |  | Insitu concrete, blinding 1(pile cap) | 3.84 | m3 | 145 | 556.8
6
| 0.08 | 3.84
2 | 4 |  | Insitu concrete, reinforced concrete, C40/50 (pile cap) | 57.6 | m3 | 145 | 8352
6
| 1.2 | 57.6
2 | 24 |  | Formwork, vertical, more than 300mm wide, class F2 | 57.6 | m2 | 115 | 6624
| 1.2 | 57.6
|  |  | Reinforcement, bar reinforcement, 16, 25, 32 & 40mm dia bars (280kg/m3) | 16.128 | tn | 1350 | 21772.8
Abutment Walls
2 | 10 |  | PCC abutment walls outer skins | 100 | m2 | 105 | 10500
| 5 | 100
2 | 4 |  | In-situ concrete, C40/50, infill to PCC walls | 340 | m3 | 145 | 49300
6
| 1 | 48
|  |  | Reinforcement, bar reinforcement, 16, 25, 32 & 40mm dia bars (200kg/m3) | 68 | tn | 1350 | 91800
Wing Walls
4 | 4.5 |  | PCC abutment walls outer skins | 108 | m2 | 200 | 21600
| 6 | 108
PCC Beams
|  |  | PCC bridge beam, type Y3, 2*20m long | 4 | no | 18000 | 72000
|  |  | PCC bridge beam, type YE3, 2 X 20m long (with integral parapet and pre-installed leading edge protection) | 2 | no | 22000 | 44000
Slab
| 45 |  | Insitu concrete, reinforced concrete, C40/50 (slab) | 81 | m3 | 145 | 11745
6
| 0.3 | 81
| 94 |  | Formwork, vertical, more than 300mm wide, class F2 | 28.2 | m2 | 115 | 3243
| 0.3 | 28.2
| 45 |  | Formwork, horizontal, more than 300mm wide, class F2 | 270 | m2 | 85 | 22950
| 6 | 270
|  |  | Reinforcement, bar reinforcement, 16, 25, 32 & 40mm dia bars (400kg/m3) | 32.4 | tn | 1350 | 43740
Parapet
2 | 45 |  | Insitu concrete, reinforced concrete, C40/50 (parapet edge upstand) | 25.2 | m3 | 145 | 3654
0.56
| 0.5 | 25.2
4 | 45 |  | Formwork, vertical, more than 300mm wide, class F2 | 25.2 | m2 | 115 | 2898
| 0.56 | 25.2
4 | 45 |  | Formwork, horizontal, more than 300mm wide, class F2 | 22.5 | m2 | 85 | 1912.5
| 0.5 | 22.5
|  |  | Reinforcement, bar reinforcement, 16, 25, 32 & 40mm dia bars (280kg/m3) | 7.056 | tn | 1350 | 9525.6
Barriers
|  |  | N2 W4 Barrier | 180 | m | 80 | 14400
|  |  | Terminals | 2 | no | 2500 | 5000
Series 2000 Waterproofing for Structures
| 45 |  | Waterproofing system to deck, spray applied system, two coats, more than 300mm wide, horizontal or up to 30º to the horizontal | 270 | m2 | 25 | 6750
| 6 | 270
| 45 |  | Waterproofing system to deck, spray applied system, two coats, 300mm wide or less at any inclination | 13.5 | m2 | 40 | 540
| 0.3 | 13.5
Series 2100 Bearings
2 | 6 | 12 | Bearings, mechanical/elastomeric type, fixed or sliding | 12 | nr | 400 | 4800
|  |  | Installation of Bearings, mechanical/elastomeric type, fixed or sliding | 12 | nr | 170 | 2040
Series 2300 Bridge Expansion Joints and Sealing of Gaps
2 | 6 | 12 | Bridge deck expansion joint, high modulus asphaltic plug joint (plan length 10m) | 12 | m | 335 | 4020
2 | 6 | 12 | Sealing of gaps, joint filler, 25mm thick | 12 | m | 10 | 120
|  |  | Joint sealant | 12 | m | 13 | 156
New Overbridge
Length 22m
Width 11m
Series 600 : Earthworks
|  |  | Excavation of acceptable material Class 5A - Topsoil (250mm thick) | 2167 | m3 | 1.65 | 3575.55
|  |  | Deposit into temporary spoil heaps | 2167 | m3 | 4.52 | 9794.84
Excavation of acceptable material excluding Class 5A
|  |  | in Cutting and Other excavation | 140 | m3 | 3.76 | 526.4
|  |  | Deposit into temporary spoil heaps | 140 | m3 | 4.52 | 632.8
Deposition of Fill
|  |  | Deposition of acceptable material taken from spoil heaps to general areas and earth bund mounds, embankments and other areas of fill (Total required = 117,137m3) | 2300 | m3 | 2.5 | 5750
|  |  | Fill with suitable material to form ramps to footbridge | 18700 | m3 | 35 | 654500
Series 500 Drainage and Service Ducts
4 | 22 | 88 | Cable duct, 1x100mm dia, depth not exceeding 1.5m, in verges and central reserves | 88 | m | 8 | 704
Series 400 Road Restraint Systems
2 | 24 | 48 | Metal parapet railings, Group P5; 1.25m | 48 | m | 450 | 21600
|  |  | Safety fence connectors | 4 | no | 175 | 700
Series 700 Pavement
| 22 |  | Tarmac | 242 | m2 | 70 | 16940
| 11 | 242
Series 1100 Kerbs, Footway and Paved Areas
Combined kerb and drainage block Beany System
Foundation to Kerbs, etc
|  |  | Mass Concrete : 450 x 150mm to kerbs | 48 | m | 8.55 | 410.4
|  |  | 100 x 100 Haunching (Per Side) | 96 | m | 0.93 | 89.28
2 | 24 | 48 | Kerbs : top block, shallow base unit, stanadard cover plate and frame: laid straight or curved exceedig 12m radius | 48 | m | 140 | 6720
Series 1600 : Piling and Embedded Retaining Walls
|  |  | Establishment of piling plant for cast in place | 1 | item | 10000 | 10000
concrete piles (CFA)
|  |  | Moving piling plant for 600mm diameter bored piles | 87 | nr | 45 | 3915
24 | 20 | 480 | Vertical 600 mm diameter cast in place piles exceeding 15m in length but not exceeding 20m in length in main piling | 480 | m | 65 | 31200
24 | 2 | 48 | Vertical 600 mm diameter empty bores in main piling (provisional allowance) | 48 | m | 35 | 1680
|  |  | Cutting off surplus length of pile (assume 2m) | 48 | m | 30 | 1440
|  |  | Preparing pile heads | 24 | nr | 30 | 720
|  |  | Establishment of proof loading equipment | 1 | item | 1700 | 1700
|  |  | Proof loading of vertical 600mm piles - say 10% | 10 | nr | 4060 | 40600
Series 1700 Structural Concrete
Pile Caps
8 x 5 x 1.2
2 | 22 |  | Insitu concrete, blinding 1(pile cap) | 38.72 | m3 | 145 | 5614.4
11
| 0.08 | 38.72
2 | 22 |  | Insitu concrete, reinforced concrete, C40/50 (pile cap) | 264 | m3 | 145 | 38280
5
| 1.2 | 264
2 | 134 |  | Formwork, vertical, more than 300mm wide, class F2 | 321.6 | m2 | 115 | 36984
| 1.2 | 321.6
|  |  | Reinforcement, bar reinforcement, 16, 25, 32 & 40mm dia bars (280kg/m3) | 79.2 | tn | 1350 | 106920
Abutment Walls
2 | 26 |  | PCC abutment walls outer skins | 260 | m2 | 105 | 27300
| 5 | 260
2 | 11 |  | In-situ concrete, C40/50, infill to PCC walls | 340 | m3 | 145 | 49300
5
| 1.2 | 132
|  |  | Reinforcement, bar reinforcement, 16, 25, 32 & 40mm dia bars (300kg/m3) | 102 | tn | 1350 | 137700
Wing Walls
4 | 16 |  | PCC abutment walls outer skins | 320 | m2 | 200 | 64000
| 5 | 320
PCC Beams
|  |  | PCC bridge beam, type Y3, 2*25m long | 9 | no | 20000 | 180000
|  |  | PCC bridge beam, type YE3, 2 X 25m long (with integral parapet and pre-installed leading edge protection) | 2 | no | 24000 | 48000
Slab
| 22 |  | Insitu concrete, reinforced concrete, C40/50 (slab) | 72.6 | m3 | 145 | 10527
11
| 0.3 | 72.6
| 134 |  | Formwork, vertical, more than 300mm wide, class F2 | 40.2 | m2 | 115 | 4623
| 0.3 | 40.2
| 22 |  | Formwork, horizontal, more than 300mm wide, class F2 | 242 | m2 | 85 | 20570
| 11 | 242
|  |  | Reinforcement, bar reinforcement, 16, 25, 32 & 40mm dia bars (400kg/m3) | 29.04 | tn | 1350 | 39204
Parapet
2 | 22 |  | Insitu concrete, reinforced concrete, C40/50 (parapet edge upstand) | 12.32 | m3 | 145 | 1786.4
0.56
| 0.5 | 12.32
4 | 22 |  | Formwork, vertical, more than 300mm wide, class F2 | 12.32 | m2 | 115 | 1416.8
| 0.56 | 12.32
4 | 22 |  | Formwork, horizontal, more than 300mm wide, class F2 | 11 | m2 | 85 | 935
| 0.5 | 11
|  |  | Reinforcement, bar reinforcement, 16, 25, 32 & 40mm dia bars (280kg/m3) | 3.4496 | tn | 1350 | 4656.96
Barriers
|  |  | N2 W4 Barrier | 640 | m | 80 | 51200
|  |  | Terminals | 8 | no | 2500 | 20000
Series 2000 Waterproofing for Structures
| 22 |  | Waterproofing system to deck, spray applied system, two coats, more than 300mm wide, horizontal or up to 30º to the horizontal | 242 | m2 | 25 | 6050
| 11 | 242
| 22 |  | Waterproofing system to deck, spray applied system, two coats, 300mm wide or less at any inclination | 6.6 | m2 | 40 | 264
| 0.3 | 6.6
Series 2100 Bearings
2 | 11 | 22 | Bearings, mechanical/elastomeric type, fixed or sliding | 22 | nr | 400 | 8800
|  |  | Installation of Bearings, mechanical/elastomeric type, fixed or sliding | 22 | nr | 170 | 3740
Series 2300 Bridge Expansion Joints and Sealing of Gaps
2 | 11 | 22 | Bridge deck expansion joint, high modulus asphaltic plug joint (plan length 10m) | 22 | m | 335 | 7370
2 | 11 | 22 | Sealing of gaps, joint filler, 25mm thick | 22 | m | 10 | 220
|  |  | Joint sealant | 22 | m | 13 | 286
Culverts
Box Culvert 1 - 900mm x 1500mm x 30m
concrete slab
0.3
2.1
30
|  | 18.9 | Insitu concrete, reinforced concrete, C40/50 (slab) | 18.9 | m3 | 145 | 2740.5
0.3
30
2
|  |  | Formwork, vertical, more than 300mm wide, class F2 | 18 | m2 | 115 | 2070
30
2.1
63
|  |  | Formwork, horizontal, more than 300mm wide, class F2 | 63 | m2 | 85 | 5355
Box Culvert
|  |  | Box Culvert - 900mm x 1500mm | 30 | m | 703.35 | 21100.5
|  |  | Headwall - 1500mm insert | 2 | nr | 5939.38 | 11878.76
Box Culvert 2 - 900mm x 1500mm x 40m
concrete slab
0.3
2.1
40
|  | 25.2 | Insitu concrete, reinforced concrete, C40/50 (slab) | 25.2 | m3 | 145 | 3654
0.3
40
2
|  |  | Formwork, vertical, more than 300mm wide, class F2 | 24 | m2 | 115 | 2760
40
2.1
84
|  |  | Formwork, horizontal, more than 300mm wide, class F2 | 84 | m2 | 85 | 7140
Box Culvert
|  |  | Box Culvert - 900mm x 1500mm | 40 | m | 703.35 | 28134
|  |  | Headwall - 1500mm insert | 2 | nr | 5939.38 | 11878.76
Box Culvert 3 - 900mm x 1200mm x 35m
concrete slab
0.3
2.1
35
|  | 22.05 | Insitu concrete, reinforced concrete, C40/50 (slab) | 22.05 | m3 | 145 | 3197.25
0.3
35
2
|  |  | Formwork, vertical, more than 300mm wide, class F2 | 21 | m2 | 115 | 2415
35
2.1
73.5
|  |  | Formwork, horizontal, more than 300mm wide, class F2 | 73.5 | m2 | 85 | 6247.5
Box Culvert
|  |  | Box Culvert - 900mm x 1200mm | 35 | m | 703.35 | 24617.25
|  |  | Headwall - 1500mm insert | 2 | nr | 5939.38 | 11878.76
Box Culvert 4 - 900mm x 2400mm x 35m
concrete slab
0.3
3
35
|  | 31.5 | Insitu concrete, reinforced concrete, C40/50 (slab) | 31.5 | m3 | 145 | 4567.5
0.3
35
2
|  |  | Formwork, vertical, more than 300mm wide, class F2 | 21 | m2 | 115 | 2415
35
3
105
|  |  | Formwork, horizontal, more than 300mm wide, class F2 | 105 | m2 | 85 | 8925
Box Culvert
|  |  | Box Culvert - 900mm x 2400mm | 35 | m | 1800 | 63000
|  |  | Headwall - 2400mm insert | 2 | nr | 8779.63 | 17559.26
Box Culvert 5 - 1200mm x 2400mm x 40m
concrete slab
0.3
3
40
|  | 36 | Insitu concrete, reinforced concrete, C40/50 (slab) | 36 | m3 | 145 | 5220
0.3
40
2
|  |  | Formwork, vertical, more than 300mm wide, class F2 | 24 | m2 | 115 | 2760
40
3
120
|  |  | Formwork, horizontal, more than 300mm wide, class F2 | 120 | m2 | 85 | 10200
Box Culvert
|  |  | Box Culvert - 1200mm x 2400mm | 40 | m | 2000 | 80000
|  |  | Headwall - 2400mm insert | 2 | nr | 8779.63 | 17559.26
Box Culvert 6 - 900mm x 1200mm x 40m
concrete slab
0.3
2.1
40
|  | 25.2 | Insitu concrete, reinforced concrete, C40/50 (slab) | 25.2 | m3 | 145 | 3654
0.3
40
2
|  |  | Formwork, vertical, more than 300mm wide, class F2 | 24 | m2 | 115 | 2760
40
2.1
84
|  |  | Formwork, horizontal, more than 300mm wide, class F2 | 84 | m2 | 85 | 7140
Box Culvert
|  |  | Box Culvert - 900mm x 1200mm | 40 | m | 703.35 | 28134
|  |  | Headwall - 1500mm insert | 2 | nr | 5939.38 | 11878.76
Box Culvert 7 - 900mm x 1200mm x 40m
concrete slab
0.3
2.1
40
|  | 25.2 | Insitu concrete, reinforced concrete, C40/50 (slab) | 25.2 | m3 | 145 | 3654
0.3
40
2
|  |  | Formwork, vertical, more than 300mm wide, class F2 | 24 | m2 | 115 | 2760
40
2.1
84
|  |  | Formwork, horizontal, more than 300mm wide, class F2 | 84 | m2 | 85 | 7140
Box Culvert
|  |  | Box Culvert - 900mm x 1200mm | 40 | m | 703.35 | 28134
|  |  | Headwall - 1500mm insert | 2 | nr | 5939.38 | 11878.76
Box Culvert 8 - 900mm x 1200mm x 30m
concrete slab
0.3
2.1
30
|  | 18.9 | Insitu concrete, reinforced concrete, C40/50 (slab) | 18.9 | m3 | 145 | 2740.5
0.3
30
2
|  |  | Formwork, vertical, more than 300mm wide, class F2 | 18 | m2 | 115 | 2070
30
2.1
63
|  |  | Formwork, horizontal, more than 300mm wide, class F2 | 63 | m2 | 85 | 5355
Box Culvert
|  |  | Box Culvert - 900mm x 1200mm | 30 | m | 703.35 | 21100.5
|  |  | Headwall - 1500mm insert | 2 | nr | 5939.38 | 11878.76
Box Culvert 9 - 900mm x 1200mm x 20m
concrete slab
0.3
2.1
20
|  | 12.6 | Insitu concrete, reinforced concrete, C40/50 (slab) | 12.6 | m3 | 145 | 1827
0.3
20
2
|  |  | Formwork, vertical, more than 300mm wide, class F2 | 12 | m2 | 115 | 1380
20
2.1
42
|  |  | Formwork, horizontal, more than 300mm wide, class F2 | 42 | m2 | 85 | 3570
Box Culvert
|  |  | Box Culvert - 900mm x 1200mm | 20 | m | 703.35 | 14067
|  |  | Headwall - 1500mm insert | 2 | nr | 5939.38 | 11878.76
PROW Works
PROW Diverisons
|  |  | Excavation of acceptable material Class 5A - Topsoil (250mm thick) | 737.5 | m3 | 1.65 | 1216.875
|  |  | Deposit into temporary spoil heaps | 737.5 | m3 | 4.52 | 3333.5
|  |  | Remove surplus acceptable material off site | 737.5 | m3 | 25 | 18437.5
|  |  | 100 mm Sub-base | 300 | m3 | 40 | 12000
|  |  | 50mm Binder Course | 2950 | m2 | 11 | 32450
|  |  | 20mm Surface Course | 2950 | m2 | 9 | 26550
|  |  | 50 x 150 flat top Pcc edging to footpaths | 1475 | m | 18 | 26550
|  |  | 100 x 100mm square bi-directional with amber corner cube | 350 | nr | 8.87 | 3104.5
3409097.22

## Series 300 Fencing (hidden)
|  | Item | Description - Long Stratton Bypass | Qty | Unit | Rate | Amount
Series 300 : Fencing
Reference Drawings :
4. 1262/BYP/004 Rev C
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 4
| 84 |  | Accoustic Fencing | 482 | m2
| 2 | 168
157
| 2 | 314
482
Post & Rail Fencing along length of Bypass
|  |  | Timber fencing to new bypass |  |  |  |  | 4002 | similar to existing so left as previous measure
2 | 3904 | 7808 | Bypass | 8276 | m |  |  | 825
DDT | [7 empty] | 534
-3 | 110 | -330 | [5 empty] | 52 | 2
|  | 7478 | [5 empty] | 246
840
[8 empty] | 313 | 3
6 | 133 | 798 | Ditto curved |  |  |  |  | 396
|  | 8276 | [5 empty] | 90 | 4
387
774
[8 empty] | 130 | 5
21
|  |  | Post & Rail Fencing along length of Link Roads |  |  |  |  | 139
125
92
|  |  | Link Roads |  |  |  |  | 466 | 6
18
2 | 52 | 104 | 2. 102 P02 | 104 | m |  |  | 48
Dated Dec 18
|  | 104 | Bypass Horizontal Aliegnment |  |  |  |  | 1494
Sheet 2
2 | 313 | 626 | 3. 103 P02 | 626 | m
Dated Dec 18
|  | 626 | Bypass Horizontal Aliegnment
Sheet 3
2 | 90 | 180 | 4. 104 P02 | 180 | m
Dated Dec 18
|  | 180 | Bypass Horizontal Aliegnment
Sheet 4
2 | 130 | 260 | 5. 105 P02 | 1014 | m
2 | 21 | 42 | Dated Dec 18
2 | 139 | 278 | Bypass Horizontal Aliegnment
2 | 125 | 250 | Sheet 5
2 | 92 | 184
0
1014
2 | 466 | 932 | 6. 106 P02 | 1064 | m
2 | 18 | 36 | Dated Dec 18
2 | 48 | 96 | Bypass Horizontal Aliegnment
Sheet 6
0
1064
Other Fencing
|  |  | Post and wire Perimeter Fence to attenuation lagoons | 1095 | m
134
| 1 | 134 | No 23
146
| 1 | 146 | No 22
154
| 1 | 154 | No.17a
149
| 1 | 149 | No.17
184
| 1 | 184 | No.14
110
| 1 | 110 | No.04a
218
| 1 | 218 | No.04
1095
| 7 |  | Gates | 7 | nr
|  |  | Post and wire Perimeter Fence to oil containment ditch | 144 | m
34
| 1 | 34 | No 22
34
| 1 | 34 | No.17
34
| 1 | 34 | Rhees Roundabout
42
| 1 | 42 | No.04
144
| 4 |  | Gates | 4 | nr

## Series 500 Drainage (hidden)
|  | Item | Description - Long Stratton Bypass | Qty | Unit | Rate | Total | Unit
Series 500 : Drainage & Service Ducts
Reference Drawings :
1. 1262/BYP/051 Rev A
Dated 15/01/18
2. 1262/BYP/052 Rev A
Dated 15/01/18
3. 1262/BYP/053 Rev B
Dated 15/01/18
4. 1262/BYP/054 Rev A
Dated 15/01/18
5. 1262/BYP/055 Rev A
Dated 05/12/17
Reference Drawings :
1. 1262/BYP/051 Rev A
Dated 15/01/18
| 3 |  | Headwalls | 3 | nr
Drains
| 140 |  | 450mm dia depth to invert nt exc 2m | 140 | m
| 70 |  | Concrete bed and surround | 70 | m
| 70 |  | Geotextile/terram route guard membrane | 546 | m2
| 5.15 | 360.5
70
| 2.65 | 185.5
546
| 70 |  | 175mm th concrete slab | 21.4375 | m3
1.75
| 0.175 | 21.4375
|  |  | Mesh reinforcement single layer; A142 | 122.5 | m2
Chambers: 1200mm int diam to the following depth range
| 4 |  | Depth nt exc 1m | 4 | nr
| 10 |  | Depth 1m to 2m | 10 | nr
Filter drains to the following diam
| 150 |  | 300mm | 150 | m
| 370 |  | 450mm | 510 | m
140
510
2. 1262/BYP/052 Rev A
Dated 15/01/18
| 7 |  | Headwalls | 7 | nr
Drains
| 74.7 |  | 225mm dia depth to invert nt exc 2m | 74.7 | m
| 9.8 |  | 300mm dia depth to invert nt exc 2m | 9.8 | m
| 83.7 |  | 450mm dia depth to invert nt exc 2m | 83.7 | m
| 120.53 |  | 600mm dia depth to invert nt exc 2m | 120.53 | m
| 15.1 |  | Contaiment ditch | 15.1 | m
| 37.35 |  | Concrete bed and surround | 37.35 | m
225mm
| 37.35 |  | Geotextile/terram route guard membrane | 250.245 | m2
| 4.75 | 177.4125 | 225mm
37.35
| 1.95 | 72.8325
250.245
| 37.35 |  | 175mm th concrete slab | 8.8239 | m3
| 1.35 |  | 225mm
| 0.175 | 8.8239
| 4.9 |  | Concrete bed and surround | 4.9 | m
300mm
| 4.9 |  | Geotextile/terram route guard membrane | 32.83 | m2
| 4.75 | 23.275 | 300mm
4.9
| 1.95 | 9.555
32.83
| 4.9 |  | 175mm th concrete slab | 1.1576 | m3
| 1.35 |  | 300mm
| 0.175 | 1.1576
| 41.85 |  | Concrete bed and surround | 41.85 | m
450mm
| 41.85 |  | Geotextile/terram route guard membrane | 326.43 | m2
| 5.15 | 215.5275 | 450mm
41.85
| 2.65 | 110.9025
326.43
| 41.85 |  | 175mm th concrete slab | 12.8166 | m3
| 1.75 |  | 450mm
| 0.175 | 12.8166
| 48.212 |  | Concrete bed and surround | 48.212 | m
600mm
| 48.212 |  | Geotextile/terram route guard membrane | 376.0536 | m2
| 5.15 | 248.2918 | 600mm
48.212
| 2.65 | 127.7618
376.0536
| 48.212 |  | 175mm th concrete slab | 16.4523 | m3
| 1.95 |  | 600mm
| 0.175 | 16.4523
|  |  | Mesh reinforcement single layer; A142 | 224.2884 | m2
| 50.4225 |  | 225
| 6.615 |  | 300
| 73.2375 |  | 450
| 0 |  | 525
| 94.0134 |  | 600
224.2884
Chambers: 1200mm int diam to the following depth range
| 2 |  | Depth nt exc 1m | 2 | nr
| 23 |  | Depth 1m to 2m | 23 | nr
Filter drains to the following diam
| 140 |  | 300mm | 270 | m
| 130 | 270
| 510 |  | 450mm | 536.05 | m
26.05
536.05
3. 1262/BYP/053 Rev B
Dated 15/01/18
| 12 |  | Headwalls | 12 | nr
Drains
| 131.23 |  | 225mm dia depth to invert nt exc 2m | 173.39 | m
| 42.16 | 173.39
| 122.7 |  | 300mm dia depth to invert nt exc 2m | 122.7 | m
| 12.6 |  | 450mm dia depth to invert nt exc 2m | 12.6 | m
| 128.8 |  | 600mm dia depth to invert nt exc 2m | 155.68 | m
| 26.88 | 155.68
| 18.7 |  | Contaiment ditch | 18.7 | m
| 86.695 |  | Concrete bed and surround | 86.695 | m
225mm
| 86.695 |  | Geotextile/terram route guard membrane | 580.8565 | m2
| 4.75 | 411.8012 | 225mm
86.695
| 1.95 | 169.0552
580.8565
| 86.695 |  | 175mm th concrete slab | 20.4817 | m3
| 1.35 |  | 225mm
| 0.175 | 20.4817
| 61.35 |  | Concrete bed and surround | 61.35 | m
300mm
| 61.35 |  | Geotextile/terram route guard membrane | 411.045 | m2
| 4.75 | 291.4125 | 300mm
61.35
| 1.95 | 119.6325
411.045
| 61.35 |  | 175mm th concrete slab | 14.4939 | m3
| 1.35 |  | 300mm
| 0.175 | 14.4939
| 6.3 |  | Concrete bed and surround | 6.3 | m
450mm
| 6.3 |  | Geotextile/terram route guard membrane | 49.14 | m2
| 5.15 | 32.445 | 450mm
6.3
| 2.65 | 16.695
49.14
| 6.3 |  | 175mm th concrete slab | 1.9294 | m3
| 1.75 |  | 450mm
| 0.175 | 1.9294
| 77.84 |  | Concrete bed and surround | 77.84 | m
600mm
| 77.84 |  | Geotextile/terram route guard membrane | 607.152 | m2
| 5.15 | 400.876 | 600mm
77.84
| 2.65 | 206.276
607.152
| 77.84 |  | 175mm th concrete slab | 26.5629 | m3
| 1.95 |  | 600mm
| 0.175 | 26.5629
|  |  | Mesh reinforcement single layer; A142 | 362.6738 | m2
| 117.0383 |  | 225
| 82.8225 |  | 300
| 11.025 |  | 450
| 0 |  | 525
| 151.788 |  | 600
362.6738
Chambers: 1200mm int diam to the following depth range
| 5 |  | Depth nt exc 1m | 5 | nr
| 25 |  | Depth 1m to 2m | 25 | nr
Filter drains to the following diam
235.9
| 77.6 |  | 300mm | 1251.5 | m
93
236.9
296.3
| 311.8 | 1251.5
4. 1262/BYP/054 Rev A
Dated 15/01/18
| 7 |  | Headwalls | 7 | nr
Drains
| 14.9 |  | 225mm dia depth to invert nt exc 2m | 14.9 | m
| 36.23 |  | 600mm dia depth to invert nt exc 2m | 36.23 | m
| 7.45 |  | Concrete bed and surround | 7.45 | m
225mm
| 7.45 |  | Geotextile/terram route guard membrane | 49.915 | m2
| 4.75 | 35.3875 | 225mm
7.45
| 1.95 | 14.5275
49.915
| 7.45 |  | 175mm th concrete slab | 1.7601 | m3
| 1.35 |  | 225mm
| 0.175 | 1.7601
| 18.115 |  | Concrete bed and surround | 18.115 | m
600mm
| 18.115 |  | Geotextile/terram route guard membrane | 141.297 | m2
| 5.15 | 93.2922 | 600mm
18.115
| 2.65 | 48.0047
141.297
| 18.115 |  | 175mm th concrete slab | 5.8647 | m3
| 1.85 |  | 600mm
| 0.175 | 5.8647
|  |  | Mesh reinforcement single layer; A142 | 43.5703 | m2
| 10.0575 |  | 225
| 33.5127 |  | 600
43.5703
Chambers: 1200mm int diam to the following depth range
| 1 |  | Depth nt exc 1m | 1 | nr
| 20 |  | Depth 1m to 2m | 20 | nr
Filter drains to the following diam
| 90 |  | 300mm | 490 | m
95
165
140
490
| 250 |  | 450mm | 510 | m
260
510
5. 1262/BYP/055 Rev A
Dated 05/12/17
| 16 |  | Headwalls | 16 | nr
Drains
| 76.2 |  | 225mm dia depth to invert nt exc 2m | 76.2 | m
| 27.6 |  | 300mm dia depth to invert nt exc 2m | 27.6 | m
| 182.4 |  | 450mm dia depth to invert nt exc 2m | 182.4 | m
| 163.3 |  | 525mm dia depth to invert nt exc 2m | 163.3 | m
| 176.8 |  | 600mm dia depth to invert nt exc 2m | 176.8 | m
| 42.9 |  | Contaiment ditch | 42.9 | m
| 38.1 |  | Concrete bed and surround | 38.1 | m
225mm
| 38.1 |  | Geotextile/terram route guard membrane | 255.27 | m2
| 4.75 | 180.975 | 225mm
38.1
| 1.95 | 74.295
255.27
| 38.1 |  | 175mm th concrete slab | 9.0011 | m3
| 1.35 |  | 225mm
| 0.175 | 9.0011
| 13.8 |  | Concrete bed and surround | 13.8 | m
300mm
| 13.8 |  | Geotextile/terram route guard membrane | 92.46 | m2
| 4.75 | 65.55 | 300mm
13.8
| 1.95 | 26.91
92.46
| 13.8 |  | 175mm th concrete slab | 3.2603 | m3
| 1.35 |  | 300mm
| 0.175 | 3.2603
| 91.2 |  | Concrete bed and surround | 91.2 | m
450mm
| 91.2 |  | Geotextile/terram route guard membrane | 711.36 | m2
| 5.15 | 469.68 | 450mm
91.2
| 2.65 | 241.68
711.36
| 91.2 |  | 175mm th concrete slab | 27.93 | m3
| 1.75 |  | 450mm
| 0.175 | 27.93
| 88.4 |  | Concrete bed and surround | 88.4 | m
600mm
| 88.4 |  | Geotextile/terram route guard membrane | 689.52 | m2
| 5.15 | 455.26 | 600mm
88.4
| 2.65 | 234.26
689.52
| 88.4 |  | 175mm th concrete slab | 30.1665 | m3
| 1.95 |  | 600mm
| 0.175 | 30.1665
| 81.65 |  | Concrete bed and surround | 81.65 | m
525mm
| 81.65 |  | Geotextile/terram route guard membrane | 571.55 | m2
| 5.2 | 424.58 | 525mm
81.65
| 1.8 | 146.97
571.55
| 81.65 |  | 175mm th concrete slab | 25.0053 | m3
| 1.75 |  | 525mm
| 0.175 | 25.0053
|  |  | Mesh reinforcement single layer; A142 | 544.9325 | m2
| 51.435 |  | 225
| 18.63 |  | 300
| 159.6 |  | 450
| 142.8875 |  | 525
| 172.38 |  | 600
544.9325
Chambers: 1200mm int diam to the following depth range
| 4 |  | Depth nt exc 1m | 4 | nr
| 36 |  | Depth 1m to 2m | 36 | nr
| 1 |  | Depth 2m to 3m | 1 | nr
Filter drains to the following diam
| 37.1 |  | 300mm | 387.8 | m
158
100
92.7
387.8
43
| 332.9 |  | 450mm | 525.9 | m
150
525.9
Existing Ditches to be Piped beneath proposed Bypass
450mm dia pipe
| 200 | 200 | 1. 1262/BYP/051 Rev A | 826.5 | m
| 26.5 | 26.5 | Dated 15/01/18
| 74.6 | 74.6 | 2. 1262/BYP/052 Rev A
| 206 | 206
| 59.4 | 59.4 | Dated 15/01/18
| 47.5 | 47.5 | 3. 1262/BYP/053 Rev B
| 71.4 | 71.4 | Dated 15/01/18
| 25.8 | 25.8 | 4. 1262/BYP/054 Rev A
| 17 | 17 | Dated 15/01/18
| 20.1 | 20.1 | 5. 1262/BYP/055 Rev A
| 78.2 | 78.2 | Dated 05/12/17
826.5
| 826.5 |  | Granular bed and surround | 826.5 | m3
| 0 |  | Selected backfill material | 0 | m3
1.15
| 0.6 | 0
1 | 720.5 |  | Permeable Geotextile membrane | 3206.225 | m2
| 4.45 | 3206.225
| 106 |  | Concrete bed and surround | 106 | m
Rerouting exisitng Ditch Incl 450mm daim pipe.
| 206 |  | Excavate to formation and dispose off site | 284.28 | m3
1.15
| 1.2 | 284.28
| 206 |  | Install Geotextile to line ditch | 1102.1 | m2
| 5.35 | 1102.1
| 206 |  | Granular bed and surround | 206 | m3
| 206 |  | 450mm diam pipe | 206 | m
| 206 |  | Backfill with suitable material | 236.9 | m3
1.15
| 1 | 236.9
Outfall By Under Road
| 15.5 | 15.5 | 300mm dia depth to invert nt exc 2m | 119.61 | m
| 15.5 | 15.5
| 15.3 | 15.3
| 11.05 | 11.05
| 15.86 | 15.86
| 15.4 | 15.4
| 15.5 | 15.5
| 15.5 | 15.5
119.61
| 11.2 | 11.2 | 525mm dia depth to invert nt exc 2m | 11.2 | m
11.2
| 13.1 | 13.1 | 450mm dia depth to invert nt exc 2m | 13.1 | m
13.1
| 59.805 |  | Concrete bed and surround | 59.805 | m
300mm
| 59.805 |  | Geotextile/terram route guard membrane | 400.6935 | m2
| 4.75 | 284.0738 | 300mm
59.805
| 1.95 | 116.6197
400.6935
| 59.805 |  | 175mm th concrete slab | 14.1289 | m3
| 1.35 |  | 300mm
| 0.175 | 14.1289
| 5.6 |  | Concrete bed and surround | 5.6 | m
525mm
| 5.6 |  | Geotextile/terram route guard membrane | 39.2 | m2
| 5.2 | 29.12 | 525mm
5.6
| 1.8 | 10.08
39.2
| 5.6 |  | 175mm th concrete slab | 1.715 | m3
| 1.75 |  | 525mm
| 0.175 | 1.715
| 6.55 |  | Concrete bed and surround | 6.55 | m
450mm
| 6.55 |  | Geotextile/terram route guard membrane | 51.09 | m2
| 5.15 | 33.7325 | 450mm
6.55
| 2.65 | 17.3575
51.09
| 6.55 |  | 175mm th concrete slab | 2.0059 | m3
| 1.75 |  | 450mm
| 0.175 | 2.0059
|  |  | Mesh reinforcement single layer; A142 | 101.9993 | m2
| 0 |  | 225
| 80.7368 |  | 300
| 11.4625 |  | 450
| 9.8 |  | 525
| 0 |  | 600
101.9993
Imported Filter Material to Filter Drains
Reference Drawings :
1. 1262/BYP/051 Rev A
Dated 15/01/18
|  |  | Imported fill ; granular material to clause 505 | 171 | m3 | )
)
| 150 |  | 300mm |  |  | )
| 0.75 |  |  |  |  | )
| 1.35 | 151.875 |  |  |  | )
| 150 |  |  |  |  | )
| 0.5 |  |  |  |  | )
| 0.16 | 12 |  |  |  | )
| 150 |  |  |  |  | )
| 0.25 |  |  |  |  | )
| 0.19 | 7.125 |  |  |  | )
|  | 171 |  |  |  | )
)
)
)
| 510 |  | Imported fill ; granular material to clause 505 |  |  | )
| 0.75 |  | 450mm | 619.65 | m3 | )
| 1.45 | 554.625 |  |  |  | )
| 510 |  |  |  |  | )
| 0.5 |  |  |  |  | )
| 0.16 | 40.8 |  |  |  | )
| 510 |  |  |  |  | )
| 0.25 |  |  |  |  | )
| 0.19 | 24.225 |  |  |  | )
|  | 619.65 |  |  |  | )
)
)
)
|  |  | 2. 1262/BYP/052 Rev A |  |  | )
|  |  | Dated 15/01/18 |  |  | )
)
| 270 |  | Imported fill ; granular material to clause 505 |  |  | )
| 0.75 |  |  | 307.8 | m3 | )
| 1.35 | 273.375 |  |  |  | )
| 270 |  | 300mm |  |  | )
| 0.5 |  |  |  |  | )
| 0.16 | 21.6 |  |  |  | )
| 270 |  |  |  |  | )
| 0.25 |  |  |  |  | )
| 0.19 | 12.825 |  |  |  | )
|  | 307.8 |  |  |  | )
)
)
| 536.05 |  | Imported fill ; granular material to clause 505 |  |  | )
| 0.75 |  | 450mm | 651.3007 | m3 | )
| 1.45 | 582.9544 |  |  |  | )
| 536.05 |  |  |  |  | )
0.5
| 0.16 | 42.884
536.05
0.25
| 0.19 | 25.4624 |  |  |  | )
|  | 651.3007 |  |  |  | )
)
)
|  |  | 3. 1262/BYP/053 Rev B |  |  | )
|  |  | Dated 15/01/18 |  |  | )
)
| 1251.5 |  | Imported fill ; granular material to clause 505 | 1426.71 | m3 | )
| 0.75 |  |  |  |  | )
| 1.35 | 1267.1438 | 300mm |  |  | )
| 1251.5 |  |  |  |  | )
| 0.5 |  |  |  |  | )
| 0.16 | 100.12 |  |  |  | )
| 1251.5 |  |  |  |  | )
| 0.25 |  |  |  |  | )
| 0.19 | 59.4462 |  |  |  | )
|  | 1426.71 |  |  |  | )
)
)
)
)
)
|  |  | 4. 1262/BYP/054 Rev A |  |  | )
)
| 490 |  | Imported fill ; granular material to clause 505 | 558.6 | m3 | )
| 0.75 |  |  |  |  | )
| 1.35 | 496.125 | 300mm |  |  | )
| 490 |  |  |  |  | )
| 0.5 |  |  |  |  | )
| 0.16 | 39.2 |  |  |  | )
| 490 |  |  |  |  | )
| 0.25 |  |  |  |  | )
| 0.19 | 23.275 |  |  |  | )
|  | 558.6 |  |  |  | )
)
)
| 510 |  | Imported fill ; granular material to clause 505 |  |  | )
| 0.75 |  | 450mm | 619.65 | m3 | )
| 1.45 | 554.625 |  |  |  | )
| 510 |  |  |  |  | )
| 0.5 |  |  |  |  | )
| 0.16 | 40.8 |  |  |  | )
| 510 |  |  |  |  | )
| 0.25 |  |  |  |  | )
| 0.19 | 24.225 |  |  |  | )
|  | 619.65 |  |  |  | )
)
)
|  |  | 5. 1262/BYP/055 Rev A |  |  | )
|  |  | Dated 05/12/17 |  |  | )
)
| 388 |  | Imported fill ; granular material to clause 505 | 442.32 | m3 | )
| 0.75 |  |  |  |  | )
| 1.35 | 392.85 | 300mm |  |  | )
| 388 |  |  |  |  | )
| 0.5 |  |  |  |  | )
| 0.16 | 31.04 |  |  |  | )
| 388 |  |  |  |  | )
| 0.25 |  |  |  |  | )
| 0.19 | 18.43 |  |  |  | )
2 |  | 442.32 |  |  |  | )
)
2 | [5 empty] | )
| 620 |  | Imported fill ; granular material to clause 505 |  |  | )
| 0.75 |  | 450mm | 753.3 | m3 | )
| 1.45 | 674.25 |  |  |  | )
| 620 |  |  |  |  | )
| 0.5 |  |  |  |  | )
| 0.16 | 49.6 |  |  |  | )
| 620 |  |  |  |  | )
| 0.25 |  |  |  |  | )
| 0.19 | 29.45 |  |  |  | )
|  | 753.3 |  |  |  | )
[6 empty] | ) | 5550.3308 | m3
Geotextile Layer to Filter Drains
2906.43
| 4.95 | 28773.657 | Permeable Geotextile membrane | 59971.677 | m2
2643.9
| 5.9 | 31198.02
59971.677
Drainage to Link Roads
Parker's lane
Drains
1 | 15.2 | 15.2 | 150mm dia depth to invert nt exc 2m (branches) | 208.15 | m
1 | 10.6 | 10.6
1 | 8.02 | 8.02
1 | 3.9 | 3.9
3 | 5.8 | 17.4
1 | 6.5 | 6.5
1 | 3.3 | 3.3
2 | 3.7 | 7.4
1 | 16.4 | 16.4
1 | 11.1 | 11.1
3 | 8.3 | 24.9
3 | 3.04 | 9.12
1 | 3.2 | 3.2
1 | 8.2 | 8.2
1 | 4.8 | 4.8
1 | 2.01 | 2.01
1 | 6.3 | 6.3
1 | 1.9 | 1.9
1 | 5.8 | 5.8
1 | 11.4 | 11.4
2 | 10.5 | 21
1 | 9.7 | 9.7
208.15
1 | 133.5 | 133.5 | 450mm dia depth to invert nt exc 2m (main run) | 411.4 | m
1 | 173.7 | 173.7
1 | 58.5 | 58.5
1 | 12.5 | 12.5
1 | 33.2 | 33.2
411.4
| 104.075 |  | Concrete bed and surround | 104.075 | m
| 0.6 |  | 150mm
| 0.45 | 28.1002
| 104.075 |  | Geotextile/terram route guard membrane | 634.8575 | m2
| 4.6 | 478.745 | 150mm
104.075
| 1.5 | 156.1125
634.8575
| 104.075 |  | 175mm th concrete slab | 21.8558 | m3
| 1.2 |  | 150mm
| 0.175 | 21.8558
| 205.7 |  | Concrete bed and surround | 205.7 | m
| 1.15 |  | 450mm
| 0.75 | 177.4162
| 205.7 |  | Geotextile/terram route guard membrane | 1604.46 | m2
| 5.15 | 1059.355 | 450mm
205.7
| 2.65 | 545.105
1604.46
| 205.7 |  | 175mm th concrete slab | 62.9956 | m3
| 1.75 |  | 450mm
| 0.175 | 62.9956
|  |  | Mesh reinforcement single layer; A142 | 484.865 | m2
| 124.89 |  | 150
| 0 |  | 300
| 359.975 |  | 450
| 0 |  | 525
| 0 |  | 600
484.865
Chambers: 1200mm int diam to the following depth range
| 12 |  | Depth 1m to 2m | 12 | nr
| 32 |  | Road Gullies | 32 | nr
| 3 |  | headwalls | 3 | nr
| 1 |  | Connection to exisitng sewer | 1 | nr
Hall Lane
Drains
1 | 10.3 | 10.3 | 150mm dia depth to invert nt exc 2m (branches) | 228.05 | m
1 | 18.2 | 18.2
2 | 7.6 | 15.2
1 | 4.7 | 4.7
2 | 2.6 | 5.2
4 | 3.8 | 15.2
4 | 5.7 | 22.8
4 | 6.6 | 26.4
4 | 2.4 | 9.6
1 | 7.6 | 7.6
1 | 17.7 | 17.7
3 | 6.4 | 19.2
3 | 2.8 | 8.4
2 | 6.5 | 13
2 | 2.2 | 4.4
1 | 19 | 19
1 | 11.15 | 11.15
228.05
1 | 139.8 | 139.8 | 450mm dia depth to invert nt exc 2m (main run) | 246.13 | m
1 | 39.3 | 39.3
1 | 67.03 | 67.03
246.13
| 114.025 |  | Concrete bed and surround | 114.025 | m
| 0.6 |  | 150mm
| 0.45 | 30.7867
| 114.025 |  | Geotextile/terram route guard membrane | 695.5525 | m2
| 4.6 | 524.515 | 150mm
114.025
| 1.5 | 171.0375
695.5525
| 114.025 |  | 175mm th concrete slab | 23.9452 | m3
| 1.2 |  | 150mm
| 0.175 | 23.9452
| 123.065 |  | Concrete bed and surround | 123.065 | m
| 1.15 |  | 450mm
| 0.75 | 106.1436
| 123.065 |  | Geotextile/terram route guard membrane | 959.907 | m2
| 5.15 | 633.7848 | 450mm
123.065
| 2.65 | 326.1223
959.907
| 123.065 |  | 175mm th concrete slab | 37.6887 | m3
| 1.75 |  | 450mm
| 0.175 | 37.6887
|  |  | Mesh reinforcement single layer; A142 | 352.1938 | m2
| 136.83 |  | 150
| 215.3638 |  | 450
352.1938
Chambers: 1200mm int diam to the following depth range
| 6 |  | Depth 1m to 2m | 6 | nr
| 34 |  | Road Gullies | 34 | nr
| 2 |  | Connection to exisitng sewer | 2 | nr
Roundabout Secondary Drainage
Drains
1 | 19.5 | 19.5 | 150mm dia depth to invert nt exc 2m (branches) | 1104.4 | m
1 | 11 | 11
1 | 11.9 | 11.9
1 | 4.7 | 4.7
1 | 10.6 | 10.6
1 | 9.6 | 9.6
1 | 11.2 | 11.2
1 | 15.2 | 15.2
1 | 13.1 | 13.1
2 | 10 | 20
1 | 7.8 | 7.8
1 | 1.5 | 1.5
1 | 25.2 | 25.2
1 | 4 | 4
1 | 26 | 26
1 | 12 | 12
3 | 6.9 | 20.7
2 | 10 | 20
1 | 13.07 | 13.07
1 | 13.9 | 13.9
1 | 25.6 | 25.6
1 | 8.3 | 8.3
1 | 15.8 | 15.8
1 | 23.06 | 23.06
1 | 5.8 | 5.8
1 | 2.7 | 2.7
1 | 8.27 | 8.27
1 | 28.7 | 28.7
1 | 14.9 | 14.9
1 | 7.1 | 7.1
1 | 19.5 | 19.5
1 | 19.2 | 19.2
1 | 18.5 | 18.5
1 | 15.8 | 15.8
1 | 22 | 22
1 | 7.8 | 7.8
1 | 10 | 10
1 | 25.4 | 25.4
1 | 10.5 | 10.5
1 | 17 | 17
1 | 1.5 | 1.5
1 | 61.3 | 61.3
1 | 67 | 67
1 | 74 | 74
1 | 18 | 18
1 | 20 | 20
1 | 14 | 14
1 | 31 | 31
1 | 12 | 12
1 | 56.1 | 56.1
1 | 33.2 | 33.2
1 | 39.2 | 39.2
1 | 41.6 | 41.6
1 | 22.5 | 22.5
1 | 16.3 | 16.3
1 | 19.8 | 19.8
1104.4
| 552.2 |  | Concrete bed and surround | 552.2 | m
| 0.6 |  | 150mm
| 0.45 | 149.094
| 552.2 |  | Geotextile/terram route guard membrane | 3368.42 | m2
| 4.6 | 2540.12 | 150mm
552.2
| 1.5 | 828.3
3368.42
| 552.2 |  | 175mm th concrete slab | 115.962 | m3
| 1.2 |  | 150mm
| 0.175 | 115.962
|  |  | Mesh reinforcement single layer; A142 | 662.64 | m2
| 662.64 |  | 150
662.64
1 | 18 | 18 | Road Gullies | 80 | nr
1 | 19 | 19
1 | 19 | 19
1 | 24 | 24
80
Miscellaneous Drainage items
3. 1262/BYP/053 Rev B
Dated 15/01/18
1 | 20.4 | 20.4 | 150mm diam pipe between ditches | 28.2 | m
1 | 7.8 | 7.8
28.2
Other drainage pipes and chambers
4. 1262/BYP/054 Rev A
|  |  | Dated 15/01/18 | 68.1 | m
1 | 68.1 | 68.1 | 150mm dia drain
68.1
| 1 |  | 1200mm diam chamber nt exc 1m deep | 1 | nr
Series 500 or 600
Stopping/Removal Up Existing Ditches
| 80.9 | 80.9 | Reference Drawings : | 1057.32 | m
| 56.7 | 56.7 | 1. 1262/BYP/051 Rev A
| 40.12 | 40.12 | Dated 15/01/18
| 72.1 | 72.1 | 2. 1262/BYP/052 Rev A
| 83.9 | 83.9 | Dated 15/01/18
| 74 | 74 | 3. 1262/BYP/053 Rev B
2 | 60.9 | 121.8 | Dated 15/01/18
| 91 | 91 | 4. 1262/BYP/054 Rev A
| 183 | 183 | Dated 15/01/18
| 129 | 129 | 5. 1262/BYP/055 Rev A
| 124.8 | 124.8
1057.32
Series 500 : Drainage & Service Ducts
Formation of Ponds ; assumed depth 3m / 45% slope sides )
|  |  | Excavation & dispose into spoil heaps | 20734.62 | m3
| 1071 |  | No.23
1
| 3 | 3213
1410
1
| 3 | 4230 | No.22
1746
1
| 3 | 5238 | No.17a
1311
1
| 3 | 3933 | No.17
1641
1
| 3 | 4923 | No.14
864
1
| 3 | 2592 | No.4a
0
1
| 3 | 0 | No.4 9 Included in above
Formation of Ponds ; assumed depth 2m / 45% slope sides )
3 | 71 |  | Oil Cotainment Ditches
1
| 3 | 639
25950.12
DDT
-0.5 | 145 |  | No.23
3
| 3 | -652.5
-0.5 | 145 |  | No.22
3
| 3 | -652.5
-0.5 | 154 |  | No.17a
3
| 3 | -693
-0.5 | 143 |  | No.17
3
| 3 | -643.5
-0.5 | 176 |  | No.14
3
| 3 | -792
-0.5 | 107 |  | No.4a
3
| 3 | -481.5
-0.5 | 218 |  | No.4
3
| 3 | -981
-0.5 | 71 |  | Oil Cotainment Ditches
3
| 3 | -319.5
20734.62
|  |  | Disposal in spoil heaps | 20734.62 | m3
|  |  | Level & compact formation | 4047 | m2
| 523 |  | No.23
| 628 |  | No.22
| 792 |  | No.17a
| 155 |  | No.17
| 748 |  | No.14
| 448 |  | No.4a
| 753 |  | No.4 9 Included in above
4047
|  |  | Pond liner | 4047 | m2
| 145 |  | Edge detail | 1159 | m
145
154
143
176
107
218
| 71 | 1159
|  |  | Allowance ecology measures | 1 | item

## Series 600 Earthworks (hidden)
|  | Item | Description - Long Stratton Bypass | Qty | Unit | Rate | Amount
Series 600 : Earthworks
Reference Drawings :
1. 1262/BYP/051 Rev A
Dated 15/01/18
2. 1262/BYP/052 Rev A
Dated 15/01/18
3. 1262/BYP/053 Rev B
Dated 15/01/18
4. 1262/BYP/054 Rev A
Dated 15/01/18
5. 1262/BYP/055 Rev A
Dated 05/12/17
5. 1262/BYP/064 Rev A
Dated 05/12/17
Topsoil Reinstatement - Class 5A
Verges
| 2906.43 |  | Bypass only over filter drains | 18864.2738 | m3
2.5
| 0.15 | 1089.9112
2643.9
2.5
| 0.15 | 991.4625
2 | 370 |  | Link Road Verges and landscaped areas
1.2
| 0.15 | 133.2 | 2. 1262/BYP/052 Rev A
540
1
| 0.15 | 81 | 2. 1262/BYP/052 Rev A
288
1
| 0.15 | 43.2 | 2. 1262/BYP/052 Rev A
2 | 485
1.2
| 0.15 | 174.6 | 3. 1262/BYP/053 Rev B
2 | 140
1.2
| 0.15 | 50.4 | 4. 1262/BYP/054 Rev A
170
1
| 0.15 | 25.5 | 4. 1262/BYP/054 Rev A
| 16275 |  | Accoustic Bund Earthwalls
1
| 1 | 16275
18864.2738
Excavations
Bypass, RBs & Link Roads
| 20845 |  | Typical Motorway Cutting generally using motorised scrapers
| 1 |  | and/or dozers on an average haul of 2000 metres (one way)
| 0.25 | 5211.25 | Excavation of acceptable material Class 5A - Topsoil | 37153.75 | m3
| 32982 |  | 250mm thick
| 1 |  |  | 247691.6667 | m2
| 0.25 | 8245.5
36315
1
| 0.25 | 9078.75
50217
1
| 0.25 | 12554.25
Attenuation Ponds
Excavation of acceptable material Class 5A - Topsoil
| 1071 |  | No.23
1
| 0.25 | 267.75
1410
1
| 0.25 | 352.5 | No.22
1746
1
| 0.25 | 436.5 | No.17a
1311
1
| 0.25 | 327.75 | No.17
1641
1
| 0.25 | 410.25 | No.14
864
1
| 0.25 | 216 | No.4a
0
1
| 0.25 | 0 | No.4 9 Included in above
3 | 71 |  | Oil Cotainment Ditches
1
| 0.25 | 53.25
37153.75
Excavation Filter drain Trench
| 150 |  | Excavation of acceptable material excluding Class 5A | 5550.3308 | m3
0.75
| 1.35 | 151.875
150
0.5
| 0.16 | 12
150
0.25
| 0.19 | 7.125
510
0.75
| 1.45 | 554.625
510
0.5
| 0.16 | 40.8
510
0.25
| 0.19 | 24.225
270
0.75
| 1.35 | 273.375
270
0.5
| 0.16 | 21.6
270
0.25
| 0.19 | 12.825
536.05
0.75
| 1.45 | 582.9544
536.05
0.5
| 0.16 | 42.884
536.05
0.25
| 0.19 | 25.4624
1251.5
0.75
| 1.35 | 1267.1438
1251.5
0.5
| 0.16 | 100.12
1251.5
0.25
| 0.19 | 59.4462
490
0.75
| 1.35 | 496.125
490
0.5
| 0.16 | 39.2
490
0.25
| 0.19 | 23.275
510
0.75
| 1.45 | 554.625
510
0.5
| 0.16 | 40.8
510
0.25
| 0.19 | 24.225
388
0.75
| 1.35 | 392.85
388
0.5
| 0.16 | 31.04
388
0.25
| 0.19 | 18.43
620
0.75
| 1.45 | 674.25
620
0.5
| 0.16 | 49.6
620
0.25
| 0.19 | 29.45
5550.3308
Forming Ditches
1 | 117.5 | 117.5 | 2.7m wide; av depth 1.00m side slopes 1:2 | 491.265 | m3
1 | 53.8 | 53.8
1 | 46.7 | 46.7
1 | 68.6 | 68.6
1 | 77.3 | 77.3
1 |  | 0
1 |  | 0
363.9
2 | 363.9 |  | Grading
| 2 | 1455.6 |  | 1455.6 | m2
SEE BULK CUTT AND FILL SPREADSHEET
|  |  | CUT | 101309.0925 | m3
|  |  | IMPORTED FILL OR FROM SPOIL HEAPS | 992.825 | m3
General
|  |  | Bund Earthworks mounds | 117137.2 | m3
|  |  | Additional imported acceptable material | 101800.3575 | m3

## Road Markings Series 1200 (hidden)
|  | Item | Description - Long Stratton Bypass | Qty | Unit | Rate | Amount
Series 1200 : Traffic Signs and Road Markings
Reference Drawings :
1. 1262/BYP/001 Rev B
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 1
2. 1262/BYP/002 Rev C
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 2
3. 1262/BYP/003 Rev B
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 3
4. 1262/BYP/004 Rev C
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 4
5. 1262/BYP/061 Rev D
Dated 05/12/17
Bypass Constructoin Details
Sheet 1
|  |  | Traffic Signs | Number | Unit
1. 1262/BYP/001 Rev B
Dated 15/01/18
| 1 |  | TSR510 Roundabout ahead 322m to give way line - single post | 1 | nr
| 1 |  | Advance directional sign 215m to give way line - triple post | 1 | nr
2. 1262/BYP/002 Rev C
Dated 15/01/18
| 3 |  | Directionnal flag sign - double post | 3 | nr
| 1 |  | Advance directional sign 70m to give way line - triple post | 1 | nr
| 1 |  | TSR510 Roundabout ahead 105m to give way line - single post | 1 | nr
2 | 1 | 2 | TSR 816 No through road - single post | 2 | nr
| 1 |  | TSR 671 - single post | 1 | nr
| 1 |  | TSR 670 - single post 30mph | 1 | nr
| 3 |  | TSR 610 - Illuminsted bollard | 3 | nr
| 3 |  | TSR 606 single post | 3 | nr
2 | 3 | 6 | TSR 515 - double post | 6 | nr
3. 1262/BYP/003 Rev B
Dated 15/01/18
| 1 |  | Advance directional sign 215m to give way line - triple post | 1 | nr
| 4 |  | TSR 610 - Illuminsted bollard | 4 | nr
| 4 |  | Directionnal flag sign - double post | 4 | nr
| 4 |  | TSR 606 single post | 4 | nr
2 | 4 | 8 | TSR 515 - double post | 8 | nr
| 2 |  | TSR 671 - single post | 2 | nr
| 2 |  | TSR 670 - single post 30mph | 2 | nr
| 1 |  | TSR510 Roundabout ahead 105m to give way line - single post | 1 | nr
| 1 |  | Advance directional sign 70m to give way line - triple post | 1 | nr
| 2 |  | Advance directional sign 215m to give way line - triple post | 2 | nr
| 2 |  | TSR510 Roundabout ahead 322m to give way line - single post | 2 | nr
4. 1262/BYP/004 Rev C
Dated 15/01/18
| 3 |  | TSR 610 - Illuminsted bollard | 3 | nr
| 3 |  | Directionnal flag sign - double post | 3 | nr
| 3 |  | TSR 606 single post | 3 | nr
2 | 3 | 6 | TSR 515 - double post | 6 | nr
| 1 |  | Advance directional sign 70m to give way line - triple post | 1 | nr
| 2 |  | TSR 671 - single post | 2 | nr
| 1 |  | TSR 670 - single post 20mph | 1 | nr
| 1 |  | TSR 670 - single post 50mph | 1 | nr
| 2 |  | Advance directional sign 160m to give way line - triple post | 2 | nr
| 2 |  | Advance directional sign 215m to give way line - double post | 2 | nr
| 1 |  | TSR510 Roundabout ahead 240m to give way line - single post | 1 | nr
| 1 |  | TSR 610 - Illuminsted bollard | 1 | nr
| 1 |  | TSR 670 - single post 30mph | 1 | nr
| 1 |  | TSR 670 - single post 50mph | 1 | nr
| 1 |  | TSR 816 No through road - single post | 1 | nr
| 1 |  | Advance directional sign 160m to give way line - triple post | 1 | nr
| 1 |  | Directionnal sign - single post | 1 | nr
4. 1262/BYP/009 Rev B
| 4 |  | TSR 610 - Illuminsted bollard | 4 | nr
| 4 |  | Directionnal flag sign - double post | 4 | nr
| 4 |  | TSR 606 single post | 4 | nr
2 | 4 | 8 | TSR 515 - double post | 8 | nr
2 | 3 | 6 | Timber bollards | 6 | nr
| 2 |  | TSR 670 - single post 30mph | 2 | nr
| 2 |  | TSR 670 - single post 50mph | 2 | nr
| 1 |  | Advance directional sign 160m to give way line - triple post | 1 | nr
| 1 |  | Advance directional sign 70m to give way line - triple post | 1 | nr
| 1 |  | TSR510 Roundabout ahead 105m to give way line - single post | 1 | nr
Traffic Signs completed
Road Markings
2 | 1160 | 2320 | 150mm wide edge marking | 6765.7 | m
| 30 | 30
| 4.8 | 4.8
| 15.29 | 15.29
2 | 600 | 1200
| 32 | 32
| 42.81 | 42.81
| 770 | 770
| 7.24 | 7.24
| 770 | 770
2 | 770 | 1540
| 33.1 | 33.1
| 1.74 | 1.74
| 31.33 | 31.33
| 27 | 27
DDT | -45.61 | -45.61
| -14 | -14
6765.7
At Roundabouts
15 | 4.1 | 61.5 | 2. 1262/BYP/002 Rev C | 1804.65 | m
3 | 18 | 54 | Dated 15/01/18
3 | 33.67 | 101.01 | Bypass Horizontal Aliegnment
12 | 2.49 | 29.88 | Sheet 2
21 | 2.7 | 56.7
3 | 5.82 | 17.46
3 | 20.6 | 61.8
15 | 4.1 | 61.5 | 3. 1262/BYP/003 Rev B
3 | 18 | 54 | Dated 15/01/18
3 | 33.67 | 101.01 | Bypass Horizontal Aliegnment
12 | 2.49 | 29.88 | Sheet 3
21 | 2.7 | 56.7
3 | 5.82 | 17.46
3 | 20.6 | 61.8
1 | 10.9 | 10.9
1 | 14.4 | 14.4
1 | 33 | 33
1 | 3.06 | 3.06
7 | 2.04 | 14.28
1 | 5.05 | 5.05
10 | 4.1 | 41 | 4. 1262/BYP/004 Rev C
2 | 18 | 36 | Dated 15/01/18
2 | 33.67 | 67.34 | Bypass Horizontal Aliegnment
8 | 2.49 | 19.92 | Sheet 4
14 | 2.7 | 37.8
2 | 5.82 | 11.64
2 | 20.6 | 41.2
1 | 10.9 | 10.9
1 | 14.4 | 14.4
1 | 33 | 33
1 | 3.06 | 3.06
7 | 2.04 | 14.28
1 | 5.05 | 5.05
5 | 4.1 | 20.5
13 | 4.1 | 53.3
2 | 23.4 | 46.8
1 | 2.96 | 2.96
2 | 1.37 | 2.74
1 | 4.74 | 4.74
1 | 2.6 | 2.6
2 | 4.35 | 8.7
1 | 11.5 | 11.5
1 | 3.85 | 3.85
15 | 4.1 | 61.5 | Northern Roundabout
3 | 18 | 54
3 | 33.67 | 101.01
12 | 2.49 | 29.88
21 | 2.7 | 56.7
3 | 5.82 | 17.46
3 | 20.6 | 61.8
3 | 4.1 | 12.3
1 | 15.2 | 15.2
1 | 16 | 16
1 | 23.5 | 23.5
1 | 4.6 | 4.6
3 | 1.6 | 4.8
1 | 2.8 | 2.8
1 | 2 | 2
1 | 2.43 | 2.43
1804.65
To the Actual Roundabout x 4
4 | 160.65 | 642.6 | 150mm white line | 642.6 | m
To Bypass and link Roads
|  |  | 150mm white line to Bybass | 3827.25 | m
Bypass
| 1045.5 |  | 1. 1262/BYP/001 Rev B |  |  |  |  | 1230 | 1045.5
| 561.85 |  | 2. 1262/BYP/002 Rev C |  |  |  |  | 661 | 561.85
| 655.35 |  | 3. 1262/BYP/003 Rev B |  |  |  |  | 771 | 655.35
| 672.35 |  | 4. 1262/BYP/004 Rev C |  |  |  |  | 791 | 672.35
Link Roads
| 0 |  | 1. 1262/BYP/001 Rev B
| 418.2 |  | 2. 1262/BYP/002 Rev C |  |  |  |  | 492 | 418.2
| 391 |  | 3. 1262/BYP/003 Rev B |  |  |  |  | 460 | 391
| 83 |  | 4. 1262/BYP/004 Rev C
3827.25
Road Studs at 18m Centres
|  |  | Bypass | 350 | nr
| 66.6667 | 67 | 1. 1262/BYP/001 Rev B
| 5 | 5 | 2. 1262/BYP/002 Rev C
| 70.2778 | 71
| 47.4444 | 48 | 3. 1262/BYP/003 Rev B
| 48.3333 | 49 | 4. 1262/BYP/004 Rev C
Link Roads
1. 1262/BYP/001 Rev B
| 28.7222 | 29 | 2. 1262/BYP/002 Rev C
| 26.6667 | 27 | 3. 1262/BYP/003 Rev B
| 6 | 6 | 4. 1262/BYP/004 Rev C
4 | 12 | 48 | Additional studs as approaching roundabouts
350
Bollards
| 7 |  | 1. 1262/BYP/001 Rev B | 17 | nr
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 1
| Incl in above |  | 2. 1262/BYP/002 Rev C
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 2
Parker's lane
| 4 |  | 3. 1262/BYP/003 Rev B
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 3
Hall Lane
| 6 |  | 4. 1262/BYP/004 Rev C
|  | 17 | Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 4

## Series 700 Bypass (hidden)
|  | Item | Description - Long Stratton Bypass | Qty | Unit | Rate | Amount
Series 700
Pavement
Reference Drawings :
1. 1262/BYP/001 Rev B
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 1
2. 1262/BYP/002 Rev C
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 2
3. 1262/BYP/003 Rev B
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 3
4. 1262/BYP/004 Rev C
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 4
5. 1262/BYP/061 Rev D
Dated 05/12/17
Bypass Constructoin Details
Sheet 1
Sub-base - Type 1 : 450mnm
Geotextile Layer x 2
Base Asphalt : 230mm
Binder Asphalt : 60mm
Surface Coat : 40mm
Approach roads
Bypass including Roundabouts
Chainage 0:000 to 3904
| 51068 |  | Sub-base - Type 1 : 450mnm | 22980.6 | m3 |  |  | was 3904
1
| 0.45 | 22980.6
| 51068 |  | Base Asphalt : 230mm | 51068 | m2
| 1 | 51068
| 51068 |  | Binder Asphalt : 60mm | 51068 | m2
| 1 | 51068
| 51068 |  | Surface Coat : 40mm | 51068 | m2
| 1 | 51068
Roundabouts (4nr New)
|  |  | Sub-base - Type 1 : 450mnm | 0 | m3
0
|  |  | Base Asphalt : 230mm | 0 | m2
0
|  |  | Binder Asphalt : 60mm | 0 | m2
0
|  |  | Surface Coat : 40mm | 0 | m2
0
Widening of Bypass Approaching Roundabout
|  |  | Sub-base - Type 1 : 450mnm | 0 | m3 |  |  | was 14
0
|  |  | Base Asphalt : 230mm | 0 | m2
0
|  |  | Binder Asphalt : 60mm | 0 | m2
0
|  |  | Surface Coat : 40mm | 0 | m2
0
DDT For Over measure on Bypass Road Through Roundabout
|  |  | Sub-base - Type 1 : 450mnm | 0 | m3
0
|  |  | Base Asphalt : 230mm | 0 | m2
0
|  |  | Binder Asphalt : 60mm | 0 | m2
0
|  |  | Surface Coat : 40mm | 0 | m2
0
ADD
Geotextile Layer x 2
2 | 51068 |  | Geotextile layer to subbase type 1 | 1009103.68 | m2
| 9.88 | 1009103.68
28 | 0
| 0 | 0
1009103.68
Traffic Islands
Parker's Lane
2. 1262/BYP/102 P02
Dated 15/01/18
| 316 |  | Sub-base - Type 1 : 100mnm | 31.6 | m3
1
| 0.1 | 31.6
| 316 |  | Binder Asphalt : 50mm | 316 | m2
| 1 | 316
| 316 |  | Surface Coat : 20mm | 316 | m2
| 1 | 316
Hall Lane
3. 1262/BYP/003 Rev B
Dated 15/01/18
|  |  | Sub-base - Type 1 : 100mnm | 0 | m3 |  |  | 61 | was 15
45
|  | 0 | [5 empty] | 50
67
223
|  |  | Binder Asphalt : 50mm | 0 | m2 |  |  |  | was 149
0
|  |  | Surface Coat : 20mm | 0 | m2
0
Adjacent Edge's Lane
4. 1262/BYP/104 P02
Dated 15/01/18
| 257 |  | Sub-base - Type 1 : 100mnm | 25.7 | m3
1
| 0.1 | 25.7
| 257 |  | Binder Asphalt : 50mm | 257 | m2
| 1 | 257
| 257 |  | Surface Coat : 20mm | 257 | m2
| 1 | 257
Link Road to Church Lane
4. 1262/BYP/004 Rev C
Dated 15/01/18
|  |  | Sub-base - Type 1 : 100mnm | 0 | m3
0
|  |  | Binder Asphalt : 50mm | 0 | m2
0
|  |  | Surface Coat : 20mm | 0 | m2
0
Northern Roundabout
4. 1262/BYP/105 P02
Dated 15/01/18
| 301 |  | Sub-base - Type 1 : 100mnm | 30.1 | m3
1
| 0.1 | 30.1
| 301 |  | Binder Asphalt : 50mm | 301 | m2
| 1 | 301
| 301 |  | Surface Coat : 20mm | 301 | m2
| 1 | 301

## Series 700 Link Road (hidden)
|  | Item | Description - Long Stratton Bypass | Qty | Unit | Rate | Amount
Series 700
Pavement
1. 1262/BYP/002 Rev C
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 2
2. 1262/BYP/064 Rev A
Dated 05/12/17
Bypass Constructoin Details
Sheet 1
Sub-base - Type 1 : 450mnm
Geotextile Layer x 2
Base Asphalt : 150mm
Binder Asphalt : 60mm
Surface Coat : 40mm
Approach roads
Link Road from New Roundabout to Parker Road
(Excluding Roundabout)
|  |  | Sub-base - Type 1 : 450mnm | 0 | m3 |  |  | Not shown
0
|  |  | Base Asphalt : 150mm | 0 | m2
0
|  |  | Binder Asphalt : 60mm | 0 | m2
0
|  |  | Surface Coat : 40mm | 0 | m2
0
Bellmouth to Park Lane
1 | 108 |  | Sub-base - Type 1 : 450mnm | 48.6 | m3
1
| 0.45 | 48.6
1 | 108 |  | Base Asphalt : 150mm | 108 | m2 |  |  | 108
| 1 | 108
1 | 108 |  | Binder Asphalt : 60mm |  | m2
| 1 | 108 |  | 108
1 | 108 |  | Surface Coat : 40mm | 108 | m2
| 1 | 108
Parkers Lane Turning Head X 2
1 | 445 |  | Sub-base - Type 1 : 450mnm | 200.25 | m3
1
| 0.45 | 200.25
1 | 445 |  | Base Asphalt : 150mm | 445 | m2 |  |  | 445
| 1 | 445
1 | 445 |  | Binder Asphalt : 60mm | 445 | m2
| 1 | 445
1 | 445 |  | Surface Coat : 40mm | 445 | m2
| 1 | 445
Church LaneTurning Head X 1
1 | 331 |  | Sub-base - Type 1 : 450mnm | 148.95 | m3
1
| 0.45 | 148.95
1 | 331 |  | Base Asphalt : 150mm | 331 | m2 |  |  | 331
| 1 | 331
1 | 331 |  | Binder Asphalt : 60mm | 331 | m2
| 1 | 331
1 | 331 |  | Surface Coat : 40mm | 331 | m2
| 1 | 331
Ipswich Road Turning Head X 1
|  |  | Sub-base - Type 1 : 450mnm | 0 | m3 |  |  | Not shown
0
|  |  | Base Asphalt : 150mm | 0 | m2
0
|  |  | Binder Asphalt : 60mm | 0 | m2
0
|  |  | Surface Coat : 40mm | 0 | m2
0
Geotextile Layer x 2
2 | 564.83 |  | Geotextile layer to subbase type 1 | 16217.614 | m2
| 7.9 | 8924.314
2 | 88.61
| 1 | 177.22
2 | 216.51
| 1 | 433.02
2 | 310.53
| 1 | 621.06
2 | 3031
| 1 | 6062
16217.614
|  |  | 1. 1262/BYP/003 Rev C |  |  |  |  | Sub-base - Type 1 : 450mnm
|  |  | Dated 15/01/18 |  |  |  |  | Geotextile Layer x 2
|  |  | Bypass Horizontal Aliegnment |  |  |  |  | Base Asphalt : 150mm
|  |  | Sheet 2 |  |  |  |  | Binder Asphalt : 60mm
|  |  | 2. 1262/BYP/064 Rev A |  |  |  |  | Surface Coat : 40mm
|  |  | Dated 05/12/17 |  |  |  |  | Approach roads
Bypass Constructoin Details
Sheet 1
Link Road from New Roundabout Replacing Existing Hall Lane
(Excluding Roundabout)
Chainage 0:000 to 485.06
| 1729 |  | Sub-base - Type 1 : 450mnm | 778.05 | m3
1
| 0.45 | 778.05
| 1729 |  | Base Asphalt : 150mm | 1729 | m2 |  |  | 1729
| 1 | 1729
| 1729 |  | Binder Asphalt : 60mm | 1729 | m2
| 1 | 1729
| 1729 |  | Surface Coat : 40mm |  | m2
| 1 | 1729
Geotextile Layer x 2
2 | 485.06 |  | Geotextile layer to subbase type 1 | 6887.852 | m2
| 7.1 | 6887.852
Edge's Lane Turning Head X 1
1 | 224 |  | Sub-base - Type 1 : 450mnm | 100.8 | m3
1
| 0.45 | 100.8
1 | 224 |  | Base Asphalt : 150mm | 224 | m2 |  |  | 224
| 1 | 224
1 | 224 |  | Binder Asphalt : 60mm | 224 | m2
| 1 | 224
1 | 224 |  | Surface Coat : 40mm | 224 | m2
| 1 | 224
Geotextile Layer x 2
2 | 224 |  | Geotextile layer to subbase type 1 | 3180.8 | m2
| 7.1 | 3180.8
Sheet 2
2. 1262/BYP/064 Rev A
Dated 05/12/17
Bypass Constructoin Details
Sheet 1
Link Road between Bypass and Church Lane
Chainage 0:000 to 485.06
| 1001 |  | Sub-base - Type 1 : 450mnm | 450.45 | m3
1
| 0.45 | 450.45
| 1001 |  | Base Asphalt : 150mm | 1001 | m2 |  |  | 1001
| 1 | 1001
0
1001
| 1001 |  | Binder Asphalt : 60mm | 1001 | m2
| 1 | 1001
0
1001
| 1001 |  | Surface Coat : 40mm | 1001 | m2
| 1 | 1001
0
1001
Geotextile Layer x 2
2 | 1221 |  | Geotextile layer to subbase type 1 | 17338.2 | m2
| 7.1 | 17338.2

## Series 1100 Kerbs Footpaths Cyc (hidden)
|  | Item | Description - Long Stratton Bypass | Qty | Unit | Rate | Amount
Series 1100 : Kerbs, Footways and Paved Areas
1. 1262/BYP/002 Rev C
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 2
2. 1262/BYP/064 Rev A
Dated 05/12/17
Bypass Constructoin Details
Sheet 1
FOOTWAYS & PAVED AREAS
Sub-base - Granular : 100mnm
Geotextile Layer x 1
Base Asphalt : NA
Binder Asphalt : 50mm
Surface Coat : 20mm
Approach roads
Footpath 2m wide (New)
| 507.991 |  | Sub-base - Type 1 : 100mnm | 1015.982 | m2
2
| 1 | 1015.982
| 507.991 |  | Binder Asphalt : 50mm | 1015.982 | m2
| 2 | 1015.982
| 507.991 |  | Surface Coat : 20mm | 1015.982 | m2
| 2 | 1015.982
Cycly/Footpath 3m wide ( Includwes Cycle path to 1st Roundabout)
| 790.11 |  | Sub-base - Type 1 : 100mnm | 2370.33 | m2
3
| 1 | 2370.33
| 790.11 |  | Binder Asphalt : 50mm | 2370.33 | m2
| 3 | 2370.33
| 790.11 |  | Surface Coat : 20mm | 2370.33 | m2
| 3 | 2370.33
Footpath 1.6m wide (Ipswick Road)
| 59.43 |  | Sub-base - Type 1 : 100mnm | 95.088 | m2
1.6
| 1 | 95.088
| 59.43 |  | Binder Asphalt : 50mm | 95.088 | m2
| 1.6 | 95.088
| 59.43 |  | Surface Coat : 20mm | 95.088 | m2
| 1.6 | 95.088
Kerbs
2 | 88 | 176 | 125 x 225 HB2 road kerbs: striaght or curved | 176 | m
1. 1262/BYP/003 Rev B
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 2
2. 1262/BYP/064 Rev A
Dated 05/12/17
Bypass Constructoin Details
Sheet 1
Footpath 2m wide (New) to Hall Lane
Chainage 38.21 to 485.06
| 446.85 |  | Sub-base - Type 1 : 100mnm | 893.7 | m2
2
| 1 | 893.7
| 446.85 |  | Binder Asphalt : 50mm | 893.7 | m2
| 2 | 893.7
| 446.85 |  | Surface Coat : 20mm | 893.7 | m2
| 2 | 893.7
Widening and Entrances to Existing Roads North Side of Road
Chainage 38.21 to 485.06
| 4.28 |  | Sub-base - Type 1 : 100mnm | 333.5922 | m2
0.97
| 1 | 4.1516
45.76
4.71
| 1 | 215.5296
4.95
2.32
| 1 | 11.484
4.96
1.28
| 1 | 6.3488
5.03
1.32
| 1 | 6.6396
6.62
2.03
| 1 | 13.4386
76
1
| 1 | 76
333.5922
| 2 |  | Binder Asphalt : 50mm | 331.3806 | m2
| 0.97 | 1.94
45.76
| 4.71 | 215.5296
4.95
| 2.32 | 11.484
4.96
| 1.28 | 6.3488
5.03
| 1.32 | 6.6396
6.62
| 2.03 | 13.4386
76
| 1 | 76
331.3806
| 4.28 |  | Surface Coat : 20mm | 333.5922 | m2
| 0.97 | 4.1516
45.76
| 4.71 | 215.5296
4.95
| 2.32 | 11.484
4.96
| 1.28 | 6.3488
5.03
| 1.32 | 6.6396
6.62
| 2.03 | 13.4386
76
| 1 | 76
333.5922
Cycly/Footpath 3m wide Soth Side of hall lane and to Roundabout)
| 430 |  | Sub-base - Type 1 : 100mnm | 1766 | m3
3
| 1 | 1290
476
1
| 1 | 476
1766
| 430 |  | Binder Asphalt : 50mm | 1766 | m2
| 3 | 1290
476
| 1 | 476
1766
| 430 |  | Surface Coat : 20mm | 1766 | m2
| 3 | 1290
476
| 1 | 476
1766
KERBS
Turning Heads
2 | 56.66 | 113.32 | 125 x 225 HB2 road kerbs: striaght or curved exc 12 m radius - Park lane | 133.32 | m
4 | 5 | 20
133.32
2 | 15.5 | 31 | 125 x 225 HB2 road kerbs: curved not exc 12 m radius | 55.6 | m
2 | 12.3 | 24.6
55.6
1 | 405 | 405 | 125 x 225 HB2 road kerbs: curved not exc 12 m radius - Ipswich road | 405 | m
Roundabouts in 4nr
Central Section
3 | 132.822 | 398.466 | 125 x 225 HB2 road kerbs: striaght or curved exc 12 m radius | 398.466 | m
Outside Section to Roundabouts
|  |  | 125 x 225 HB2 road kerbs: striaght or curved exc 12 m radius | 1549.87 | m
| 326.3 |  | Southend Roundabout - Parkers Lane
|  |  | Hall Lane Roundabout |  |  |  |  | 466
| 382.32 |  | Rhees Green Roundabout
| 841.25 |  | Northend Roundabout. A140 in both directions and entrance to site
1549.87
Link Road Kerbs
|  |  | 125 x 225 HB2 road kerbs: striaght or curved exc 12 m radius | 2268.54 | m
2 | 497.33 | 994.66 | Parkers Lane
| 103.98 | 103.98 | Parkers Lane
| 21.26 | 21.26 | Parkers Lane
2 | 417.75 | 835.5 | Hall Lane
| 8.73 | 8.73 | Hall Lane
| 345.7 | 345.7 | Leading to Church Lane
|  | 0 | Rhees Green incl in outside section of roundabout
DDT | -41.29 | -41.29 | Parkers Lane
2268.54
125 x 225 HB2 road kerbs: curved not exc 12 m radius
| 21.07 |  | Parkers Lane | 28.57 | m
| 7.5 | 28.57 | Leading to Church Lane
Edge Kerbs to Link Roads
|  |  | 150 X 50 flat top edge kerbs | 2388.76 | m
2 | 497.33 | 994.66 | Parkers Lane
| 103.98 | 103.98 | Parkers Lane
| 21.26 | 21.26 | Parkers Lane
| 114.22 | 114.22 | Parkers Lane
2 | 417.75 | 835.5 | Hall Lane Roundabout |  |  |  |  | 2
| 8.73 | 8.73
| 6 | 6
| 345.7 | 345.7 | Leading to Church Lane
DDT | -41.29 | -41.29 | Parkers Lane
2388.76
Edge Kerbs to Roundabouts
|  |  | 150 X 50 flat top edge kerbs | 1548.23 | m
| 217.28 |  | Parkers Lane
| 227 |  | Hall Lane Roundabout |  |  |  |  | 227
| 258.7 |  | Rhees Green Roundabout
| 845.25 |  | Northend Roundabout. A140 in both directions and entrance to site
1548.23
Road Kerbs to Islands
|  |  | 125 x 225 HB2 road kerbs: striaght or curved exc 12 m radius | 631.6528 | m
2 | 39.35 | 78.7 | Southend Roundabout - Parkers Lane
1 | 28.3728 | 28.3728 | Southend Roundabout - Parkers Lane
| 240 | 240 | Hall Lane Roundabout |  |  |  |  | 137
| 107.46 | 107.46 | Rhees Green Roundabout
| 39.67 | 39.67 | Leading to Church LAne
| 137.45 | 137.45 | Northend Roundabout
631.6528
Dropped Kerbs
4 | 1.84 | 7.36 | 1. 1262/BYP/001 Rev B | 169.28 | m
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 1
24 | 1.84 | 44.16 | 2. 1262/BYP/002 Rev C
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 2
32 | 1.84 | 58.88 | 3. 1262/BYP/003 Rev B
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 3
32 | 1.84 | 58.88 | 4. 1262/BYP/004 Rev C
|  | 169.28 | Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 4
Bullnosed Kerbs
4 | 1.84 | 7.36 | 1. 1262/BYP/001 Rev B | 169.28 | m
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 1
24 | 1.84 | 44.16 | 2. 1262/BYP/002 Rev C
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 2
32 | 1.84 | 58.88 | 3. 1262/BYP/003 Rev B
Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 3
32 | 1.84 | 58.88 | 4. 1262/BYP/004 Rev C
|  | 169.28 | Dated 15/01/18
Bypass Horizontal Aliegnment
Sheet 4
Tactile Paving Slabs
46 | 1.8 |  | 450x 450 x 50mm slabs | 74.52 | m2
| 0.9 | 74.52

## Sheet1 (hidden)
Drainage Ditch from Railway Line to edge of Carpark
Excavate to formation and dispose off site | 602 | m | 30 | 18060
Grade ditch to form slopes and base | 925 | m2 | 5 | 4625
Install Geotextile to line ditch | 925 | m2 | 3 | 2775
Granular fill | 366 | m3 | 35 | 12810
Carrier pipe to base of ditch | 215 | m | 0 | 0
Drainage to car park areas
Includes allowance for drainage under car park & bus areas (no details) | 7786 | m2 | 5 | 38930
Connection pipes from under road and footpath | 117 | m | 180 | 21060
Connection pipes | 167 | m | 60 | 10020
Carrier pipe to collect carpark drainage | 161 | m | 165 | 26565
Junctions / Connection to carrier pipes | 4 | nr | 25 | 100
Connection to Ditch / pond (headwall) | 15 | nr | 30 | 450
Petrol interceptors | 2 | nr | 2000 | 4000
Pcc pipe culvert under access road for waterway | 15 | m | 250 | 3750
Slab to protect | 30 | m2 | 90 | 2700
Formation of Ponds ; assumed depth 2m / 45% slope sides )
Excavation | 3783 | m3 | 5 | 18915
Disposal off-site | 3783 | m3 | 25 | 94575
Level & compact formation | 2450 | m2 | 1 | 2450
Pond liner | 2450 | m2 | 4 | 9800
Stone lining ; allow 250mm layer | 613 | m3 | 50 | 30650
Edge detail | 305 | m | 12 | 3660
Allowance ecology measures | 1 | item | 5000 | 5000 | 165050 | 43.6294

## Cut & Fill Quants (hidden)
Cut & Fill Quants